## UP BAGUIO
OFFICE OF THE VICE PRESIDENT FOR DEVELOPMENT
INFRASTRUCTURE PROJECTS
OCTOBER 2014
UP BAGUIO | [13 empty] | 100
| PROJECT | PROJECT DESCRIPTION | DESIRED PROJECT OUTCOME | BUDGET (PhP) | CONTRACT PRICE (PhP) | ACTUAL COST (PhP) | SOURCE OF FUNDS | Contractor/Vendor | No. of Biddings | Date of Notice of Award | Date of Notice to Proceed | TARGET START DATE | ACTUAL START DATE | % ACCOMPLISHMENT | TARGET COMPLETION DATE | ACTUAL COMPLETION DATE | REMARKS (Problems/Issues Encountered and Other Pertinent Information Regarding the Project) | Status | PROGRESS BILLING 1 | PROGRESS BILLING 2 | PROGRESS BILLING 3 | PROGRESS BILLING 4 | PROGRESS BILLING 5 | PROGRESS BILLING 6 | PROGRESS BILLING 7 | PROGRESS BILLING 8 | PROGRESS BILLING 9 | PROGRESS BILLING 10
1 | Renovation, Expansion, and Repainting of the Residence Hall | Renovation, Expansion & Repainting of Residence Hall | Improved access to on-campus accommodation for UP students | 11385000 |  | 11395725 | 2012 CHED Funding |  | 1 | 2012-12-11 | 2013-01-28 | 2013-01-28 | 2013-01-28 | 100 | 2013-07-27 | 2013-10-27 | Payment completed | Completed
2 | Extension of Human Kinetics Program Building | Extension of Human Kinetics Program Building | Enhanced learning environment; improved access to academic support facility | 3960000 |  | 3084788 | 2012 CHED Funding |  | 1 | 2012-12-14 | 2013-02-04 | 2/4/2013 | 2013-02-07 | 100 | 2013-08-06 | 2014-02-10 | Payment in process - COA inspection report pending | Completed
3 | Extention of the College of Arts & Communication Building | Extension of the College of Arts & Communication Building | Enhanced learning environment | 7920000 |  | 5996395 | 2012 CHED Funding |  | 1 | 2012-12-11 | 2013-01-21 | 2013-01-21 | 2013-01-21 | 100 | 2013-08-19 | 2013-12-19 | Payment completed | Completed
4 | Demolition & Conversion of Psychology Building to Additional Lab Rooms and Extention of Kolehiyo ng Agham Building | Demolition & Conversion of Psychology Building to Additional Lab Rooms and Extension of Kolehiyo ng Agham Building | Enhanced learning environment; improved access to academic support facility | 8415000 |  | 7106900 | 2012 CHED Funding |  |  | 2012-12-11 | 2013-01-21 | 2013-01-21 | 2013-01-21 | 100 | 2013-08-19 | 14-Jan-14_Orig Contract; 22Feb14_Add'l/ Variation Contract | Payment of the Project completed - Additional/Variation payment in process | Completed
5 | Extension & Repainting of the Galerya Kordilyera | Extension & Repainting of the Galerya Kordilyera | Enhanced learning environment; improved access to academic support facility | 9900000 |  | 8105183 | 2012 CHED Funding |  | 1 | 2012-12-11 | 2013-01-21 | 2013-01-21 | 2013-01-21 | 100 | 2013-08-19 | 2013-10-29 | Payment completed | Completed
6 | Completion of Various Academic Buildings & Facilities | Completion of Various Academic Buildings & Facilities | Enhanced learning environment | 60500000 |  |  | 2014 CO Budget | [6 empty] | 0
7 | Establishment of the Cordillera Gallery-Museum within the UP Baguio Cultural Hub | Establishment of the Cordillera Gallery-Museum (within the UP Baguio Cultural Hub) to showcase the rich, natural and artistic wealth of the Cordillera region; and to house the research and creative work/output of the Faculty | Modern Auditorium fully integrated with the Cordillera Museum | 26100000 | 21,160,000.00 (Infrastructure) 4,940,000.00 (Equipment) | 18,500,629.00 (Infrastructure) | 2014 CO Budget (CIDP) | MIG-WELLS CORPORATION | 1 | 2015-02-20 |  |  |  | 25 |  |  | - Construction started in March 2015 - Original bidder was disqualified - Project to be awarded to the 2nd lowest bidder - Status updated as of 11 May 2015
8 | Construction of the UP Baguio International House | Phase I of the construction of the UP Baguio International House | Improved support facilities and services for UP visiting professors, UPB faculty and international students | 20000000 |  |  | 2015 CO Budget (NEP) | [6 empty] | 0 |  |  | Schematic design at 30% (updated as of 11 May 2015)
9 | Establishment of Green Campus | Establishment of a materials recovery facility, water treatment plant, enhancement of rainharvesting facilities and other recycling infrastructure | Improved and eco-friendly environment for UP students, faculty, staff and other stakeholders | 29500000 |  |  | 2015 CO Budget (NEP) | [6 empty] | 0 |  |  | Schematic design at 20% (updated as of 11 May 2015)
10 | Construction of Montaine Field Station in Mt. Sto. Tomas Utilizing Green Architecture, Suitable for Geology Research | Construction of the Montaine Research Field Station utilizing green architecture | Enhanced research environment and increased research productivity | 1000000 |  |  | 2015 CO Budget (NEP) | [6 empty] | 0 |  |  | Currently in its Design Phase Status updated as of 13 May 2015
11 | Procurement of Various Equipment for the College of Science | Procurement of Various Equipment for the College of Science | Enhanced learning/research environment and increased research productivity | 8000000 |  |  | UP System RF | [6 empty] | 0 |  | 2011 |  | Completed
12 | College of Science Finishing & Lab Improvement | Provision of laboratory fixtures, furnishing and equipment for the KA Center for Research in the Natural Sciences and Mathematics | Enhanced learning/research environment and increased research productivity | 10000000 |  |  | UP System RF | [6 empty] | 0 |  |  | Budget earmarked on 07 Jan 2014
13 | Extension of Kolehiyo ng Agham Building |  |  | 5940000 | [9 empty] | 0
14 | Demolition of Old Psychology Building to Additional Rooms |  |  | 2475000 | [9 empty] | 0
0
1 | Design |  |  |  | 113850 |  |  | Arch. Aristotle Go | [5 empty] | 0
1 | Structural Consultancy Service |  |  |  | 13169 |  |  | Palma & Agpad | [5 empty] | 0
1 | Construction |  |  |  | 9730082 |  |  | Welmary Construction & Supply | [5 empty] | 0
2 | Design & Development Consultancy Service |  |  |  | 39600 |  |  | Arch. Aristotle Go | [5 empty] | 0
2 | Structural Consultancy Service |  |  |  | 4580 |  |  | Palma & Agpad | [5 empty] | 0
2 | Construction |  |  |  | 3040608 |  |  | IRC Construction & Supply | [5 empty] | 0
3 | Design & Development Consultancy Service |  |  |  | 79200 |  |  | Arch. Aristotle Go | [5 empty] | 0
3 | Structural Consultancy Service |  |  |  | 9161 |  |  | Palma & Agpad | [5 empty] | 0
3 | Construction |  |  |  | 5908034 |  |  | CAD Construction | 1 |  |  |  |  | 0
4 | Design & Development Consultancy Service |  |  |  | 99000 |  |  | Arch. Aristotle Go | [5 empty] | 0
4 | Structural Consultancy Service |  |  |  | 11451 |  |  | Palma & Agpad | [5 empty] | 0
4 | Construction |  |  |  | 6996449 |  |  | CAD Construction | [5 empty] | 0
5 | Design & Development Consultancy Service |  |  |  | 99000 |  |  | Arch. Aristotle Go | [5 empty] | 0
5 | Structural Consultancy Service |  |  |  | 11451 |  |  | Palma & Agpad | [5 empty] | 0
5 | Construction |  |  |  | 7994732 |  |  | Plano Builders | [5 empty] | 0
6 | Completion of the Construction of the Mini-Theater as the Extension of the College of Arts & Communication | The College of Arts and Communication Theatre will serve as venue for performances and academic fora. | Enhanced learning environment |  | 13577000 | 11483211.99 |  | WELMARY CONSTRUCTION AND SUPPLY | 1 | 2014-12-10 | 2015-01-29 | 2015-01-29 | 2015-01-29 | 0 | 2015-08-27 |  | Bidding completed; Notice of Award, Notice to Proceed issued (construction is on-going) | On-going
6 | Completion of the Kolehiyo ng Agham Building | Research Center in the Natural Sciences and Mathematics | Enhanced learning environment |  | 12383000 | 11073405.12 |  | CAD CONSTRUCTION | 1 | 2014-12-01 | 2015-01-29 | 2015-01-29 | 2015-01-29 | 0 | 2015-08-27 |  | Bidding completed; Notice of Award, Notice to Proceed issued (construction is on-going) | On-going
6 | Completion of the Extension and Repainting of Galerya Kordilyera | Galerya Kordilyera to house the Museo Kordilyera (Cordillera Ethnographic Museum) | Enhanced learning environment and support the niche of UP Baguio in Cordillera studies |  | 17460000 | 14556748.9 |  | GREAT ZONE ENTERPRISE | 1 | 2014-05-12 | 2014-12-04 | 2014-12-04 | 2014-12-04 | 0 | 2015-07-02 |  | Bidding completed; Notice of Award, Notice to Proceed issued (construction is on-going) | On-going
6 | Expansion of the Human Kinetics Program Building into a Gymnasium | HKP building with Gymnasium and a fullsized ball court | Enhanced learning environment and varsity sports program |  | 17080000 | 15260395.35 |  | ACCURACY BUILDER ENTERPRISE | 1 | 2015-02-17 |  |  |  | 0 |  |  | Bidding completed; Notice of Award and contract issued, Pre-Construction Meeting on March 9, 2015 before start of the project | Construction starts on March 2015
Formulas:
TARGET START DATE = [Date of Notice to Proceed]
ACTUAL START DATE = [TARGET START DATE]