## UP CEBU
OFFICE OF THE VICE PRESIDENT FOR DEVELOPMENT
INFRASTRUCTURE PROJECTS
OCTOBER 2014
UP CEBU | [13 empty] | 100
| PROJECT | PROJECT DESCRIPTION | DESIRED PROJECT OUTCOME | BUDGET (PhP) | CONTRACT PRICE (PhP) | ACTUAL COST (PhP) | SOURCE OF FUNDS | Contractor/Vendor | No. of Biddings | Date of Notice of Award | Date of Notice to Proceed | TARGET START DATE | ACTUAL START DATE | % ACCOMPLISHMENT | TARGET COMPLETION DATE | ACTUAL COMPLETION DATE | REMARKS (Problems/Issues Encountered and Other Pertinent Information Regarding the Project) | PROGRESS BILLING 1 | PROGRESS BILLING 2 | PROGRESS BILLING 3 | PROGRESS BILLING 4 | PROGRESS BILLING 5 | PROGRESS BILLING 6 | PROGRESS BILLING 7 | PROGRESS BILLING 8 | PROGRESS BILLING 9 | PROGRESS BILLING 10
1 | Construction of the UPPS-Cebu SRP Building & Auditorium | Construction of a new building for the UP Professional Schools at Cebu SRP, to offer graduate programs in business administration, IT and related fields | Enhanced learning environment | 63000000 | 62586819 | 63004502 | UP System RF, SARO-Senator Sergio Osmeña | Ce Padilla Construction Inc. | 1 | 2011-11-08 | 2011-11-24 | 2011-11-25 | 2011-12-05 | 100 | 2012-12-21 | 2012-12-15 | Completed as of Dec 2012 | 2012-03-06 | 2012-07-05 | 12/21/2012. Final billing | 4/19/2013, variation order
2 | Modernization of UP Cebu Science Lab & Expansion of Computer Lab Equipment | Modernization of UP Cebu Science Lab & Expansion of Computer Lab Equipment | Enhanced learning/research environment and increased research productivity | 12870000 | 12179653 |  | 2012 CHED Funding | Various suppliers | [5 empty] | 99 |  |  | Ongoing Status updated as of 11 May 2015
3 | Design & Construction of the UP Cebu Library at Lahug | Design & Construction of the UP Cebu Library at Lahug | Enhanced learning/research environment and increased research productivity | 49500000 |  |  | 2012 CHED Funding | Rex E. Morales Construction | 2 |  |  |  |  | 100 |  |  | Completed as of 08 May 2015
4 | Design & Construction of the UP Cebu Library at SRP | Design & Construction of the UP Cebu Library at SRP | Enhanced learning/research environment and increased research productivity | 49500000 |  |  | 2012 CHED Funding |  | 1 |  |  |  |  | 35 |  |  | Ongoing Status updated as of 11 May 2015
5 | UP Cebu High School Building | Construction of a new building for the UP Cebu High School | Enhanced learning environment | 60000000 | 54335583.99 |  | 2013 CO Budget | A. A. Masong Construction | [5 empty] | 0 |  |  | NTP has been issued; work cannot proceed because the area needs to be cleared of informal settlers
6 | Design & Construction of Arts & Sciences Building Extension | Design & Construction of Arts & Sciences Building Extension | Enhanced learning environment | 13000000 | 12995698.05 |  | 2014 CO Budget (CIDP) | Maqueserg Construction and General Merchandise | 2 | 2015-01-20 | 2015-02-23 |  |  | 26.67 |  |  | NOA issued on 20 Jan 2015 NTP issued on 23 Feb 2015 Design phase complete Contractor now applying for Locational Clearance from the city zoning department Status updated as of 11 May 2015
7 | Expansion of the Mini Gallery & Refurbishment of the UP Cebu Conference Hall & AVR into the UP Cebu Performing Arts Hall | Expansion of the Mini Gallery & Refurbishment of the UP Cebu Conference Hall & AVR into the UP Cebu Performing Arts Hall | Improved access to academic support facilities and services for UP faculty, students & staff | 8400000 | 808632.82 |  | 2014 CO Budget (CIDP) | Maqueserg Construction and General Merchandise | 1 | 2014-12-18 | 2015-02-23 |  |  | 61.4 |  |  | NOA issued on 18 Dec 2014 NTP issued on 23 Feb 2015 Contractor for the Performing Arts Hall is going through the punchlist and will submit their final billing within May 2015. Status updated as of 11 May 2015
8 | Repair, Rehabilitation & Renovation of Various Classrooms, Labs & Offices | Repair, Rehabilitation & Renovation of Various Classrooms, Labs & Offices | Enhanced learning/research environment and increased research productivity | 6190000 |  |  | 2015 CO Budget (NEP) | [6 empty] | 0 |  |  | For Purchase Request/JO preparation
9 | Construction of UP Cebu Guesthouse Building in UPD |  |  | 2600000 | 2615725 |  | UP Cebu RF |  | 1 |  |  |  |  | 0 |  |  | Pre-Bid Conference conducted on 02 Mar 2015 Bid Opening conducted on 16 Mar 2015
10 | Construction of Classrooms-Existing UP Cebu High School |  |  | 4500000 |  |  | 2014 DPWH Budget | La Prueba Construction | [5 empty] | 0 |  |  | Design by DPWH architect needed revision since it would cost more than P4.5M budget
11 | Renovation of Existing UP High School Buildings | Renovation, rehabilitation and repair of existing UP Cebu High School building | Enhanced learning environment | 3000000 |  |  | 2014 DPWH Budget | La Prueba Construction | [5 empty] | 90 |  |  | For final acceptance by End-user
12 | Construction of 2 Wings at 8 Stories per Wing to House Administrative Offices, as well as Clusters/Colleges: Phases 1&2 |  |  | 400000000 |  |  |  | N/A | [5 empty] | 0 |  |  | Proposal stage
13 | Marquee Room/Covered Gymnasium |  |  | 30000000 |  |  |  | N/A | [5 empty] | 0 |  |  | Design stage
14 | Library/Learning Commons-Phase 2 |  |  | 30000000 |  |  |  | N/A | [5 empty] | 0 |  |  | Proposal stage
15 | Construction of 2 storey BMC Building |  |  | 9000000 | [9 empty] | 0 |  |  | For Purchase Request/JO preparation
16 | Renovation of Fine Arts Workshop | [12 empty] | 100 |  | 2015-05-12 | Completed as of 12 May 2015
17 | Installation of Net for the Goal Post at Soccer Field | [12 empty] | 100 |  | 2015-05-12 | Completed as of 12 May 2015
18 | Repair of Collapsed Fence at the back of UGSD Building | [12 empty] | 100 |  | 2015-05-12 | Completed as of 12 May 2015
0
18 | Soil Testing |  |  |  | 137480 |  |  | E.B. Testing Center | [5 empty] | 100 |  | 2013-12-31 | Completed as of 31 Dec 2013
18 | Design and Construction |  |  |  | 72698979.88 |  |  | C.E. Padilla Construction Inc. | [5 empty] | 35 |  |  | Status updated as of 11 May 2015