## UP DILIMAN
OFFICE OF THE VICE PRESIDENT FOR DEVELOPMENT
INFRASTRUCTURE PROJECTS
OCTOBER 2014
UP DILIMAN | [13 empty] | 100
| PROJECT | PROJECT DESCRIPTION | DESIRED PROJECT OUTCOME | BUDGET (PhP) | CONTRACT PRICE (PhP) | ACTUAL COST (PhP) | SOURCE OF FUNDS | Contractor/Vendor | No. of Biddings | Date of Notice of Award | Date of Notice to Proceed | TARGET START DATE | ACTUAL START DATE | % ACCOMPLISHMENT | TARGET COMPLETION DATE | ACTUAL COMPLETION DATE | REMARKS (Problems/Issues Encountered and Other Pertinent Information Regarding the Project) | PROGRESS BILLING 1 | PROGRESS BILLING 2 | PROGRESS BILLING 3 | PROGRESS BILLING 4 | PROGRESS BILLING 5 | PROGRESS BILLING 6 | PROGRESS BILLING 7 | PROGRESS BILLING 8 | PROGRESS BILLING 9 | PROGRESS BILLING 10
1 | NIMBB Civil Works & Installation of FCUs | Civil works and installation of fan coil units | Enhanced research environment and increased research productivity | 1485000 | 1441684 |  | 2012 CHED Funding | Enrivel Construction | [5 empty] | 100 |  | 2014-05-19 | Completed as of 19 May 2014
2 | Renovation of UP Diliman Police Headquarters | Renovation and rehabilitation of existing UP Diliman Police Headquarters building | Improved campus security & safety | 4950000 | 3830657 |  | 2012 CHED Funding | Three W Builders | [5 empty] | 100 |  | 2013-11-25 | Completed as of 25 Nov 2013
3 | Conversion of CMC Film Department to CMC Library-Plaridel Hall | Conversion of CMC Film Department to CMC Library | Enhanced learning environment | 4950000 | 4702901 |  | 2012 CHED Funding | Reygem Builders |  |  | 2013-02-20 |  |  | 100 |  | 2013-10-31 | Completed as of 31 Oct 2013
4 | School of Statistics Building-Phase 1 | Construction of a new building for the School of Ststistics (Phase 1) | Enhanced learning environment | 73078722.74 | 49500000 |  | 2012 CHED Funding, UP System RF | Accuracy Builders |  |  | 2013-05-28 |  |  | 96 | 2014-11-30 |  | From Engr. Philip of OCA: For punchlisting - Status updated as of 15 May 2015
5 | Renovation of EEE Building 1 | Renovation and rehabilitation of the Institute of Electronic and Electrical Engineering building | Enhanced learning/research environment and increased research productivity | 6930000 | 5198603 |  | 2012 CHED Funding | Mechanics Construction Corporation |  |  | 2013-02-19 |  |  | 100 |  | 2015-04-01 | Completed as of 01 April 2015
6 | Completion of IESM Auditorium | Construction of the Institute of Environmental Science and Meteorology building | Enhanced learning/research environment and increased research productivity | 2970000 | 2535605 |  | 2012 CHED Funding | Three W Builders |  |  |  |  | 2013-05-23 | 100 |  | 2014-06-30 | completed as of 30 Jun 2014
7 | Completion of Toilets & Landscaping Works-Institute of Chemistry | Renovation and rehabilitation of toilets and landscaping of the Institute of Chemistry building | Enhanced learning/research environment and increased research productivity | 3960000 | 3010826 |  | 2012 CHED Funding | Jesus Asuncion Builders | [5 empty] | 100 |  | 2013-07-16 | Completed as of 16 Jul 2013
8 | National Science Complex Student Center | Constructiono of the student center at the National Science Complex | Improved access to academic support facilities and services for UP students | 4455000 | 4374535 |  | 2012 CHED Funding | Three W Builders |  |  |  | 2013-05-23 |  | 5 |  |  | - Original target start date: 23 May 2013 - construction not started as of 31 Oct 2014; work suspended; - contractor cannot mobilize; awaiting completion of demolition of existing structure (NIGS motor pool) and hauling of debris - Construction work has resumed on 01 Mar 2015
9 | Construction of Academic Building 1 (Phase 3), Partial Site Development and Completion of Multi-Purpose Building, UPEPP | Construction of the building (Phase 1) for the UP Extension Program in Pampanga, Clark | Enhanced learning environment | 99000000 | 68555478 |  | 2012 CHED Funding | Accuracy Builders |  |  | 2013-07-19 |  |  | 89 |  |  | Work stopped due to variation order & DAP issue Status updated as of 11 May 2025
10 | Renovation of UP Pep Squad Room/Dance Studio, University Theater | Renovation and rehabilitation of the UP Pep Squad Room and the dance studio at the University Theater | Improved access to academic support facilities for UP students | 1485000 | 1398016 |  | 2012 CHED Funding | PGM Construction | [5 empty] | 100 |  | 2013-08-01 | Completed as of 01 Aug 2013
11 | Structured Cabling of Various NSC Buildings-IB, IM & IESM |  |  | 1782000 |  |  | 2012 CHED Funding |  | 4 |  |  |  |  | 0 |  |  | - Two failed biddings due to post-disqualification of lone bidder; - no bidders during the third public bidding held on 19 Dec 2013 - total of four biddings have failed
12 | Renovation of Residence Halls | Renovation, rehabilitation and repair of various rooms/units/facilities of existing dormitories in UP Diliman | Improved access to on-campus accommodation for UP students | 49500000 | 24764390 | [8 empty] | 0
13 | NIGS Electrical Upgrading & NSC Miscellaneous Works | Renovation, rehabilitatio and upgrading of electrical systems and other utilities at the National Institute of Geological Sciences | Enhanced learning/research environment and increased research productivity | 5940000 | 5362615 |  | 2012 CHED Funding | Jesus Asuncion Builders | [5 empty] | 100 |  | 2014-04-01 | Completed as of 01 Apr 2014
14 | Lighting System Works for Open Air Assembly | Installation of a new eco-friendly lighting system in open assembly areas of UP Diliman | Improved campus security & safety | 1485000 | 813434 |  | 2012 CHED Funding | Mechanics Construction Corporation | [5 empty] | 100 |  | 2014-01-13 | Completed as of 13 Jan 2014
15 | National Science Complex Site Development | Construction/rehabillitation of the National Science Complex immediate vicinity/premises | Improved access to academic support facilities for UP students | 7425000 | 5852916 | [8 empty] | 0
16 | Waterline Re-piping of Various Buildings | Repair and rehabilitation of water utility system in various buildings of UP Diliman | Improved working environment for UP administrators and stakeholders | 1683000 | 1548379 |  | 2012 CHED Funding | PGM Construction | [5 empty] | 98 |  |  | - Work resumed on 10 Feb 2014 following an earlier suspension of work due to variation order - Status updated as of 11 May 2015
17 | Installation of Solar-Powered LED Streetlights | Installation of new and eco-friendly lights along the campus streets/walkways | Safer and eco-friendly working environment for UP administrators and stakeholders | 2935350 | 2935350 |  | 2012 CHED Funding | People's International Enterprises Company |  |  | 2014-01-14 |  |  | 0 |  |  | Request to transfer to another location except Quezon Hall issued Status updated as of 11 May 2015
18 | Palma Hall Pavilions Renovation | Renovation and rehabilitation of the Palma Hall pavilions | Enhanced learning environment | 71314650 | 57690674.24 | [8 empty] | 0
19 | College of Fine Arts: Repair/Rehabilitation of Bartlet Annex | Renovation, rehabilitation and repair of various rooms/units/facilities of the College of Fine Arts building | Enhanced learning/research environment and increased research productivity | 7000000 |  |  | 2014 CO Budget | [6 empty] | 0 |  |  | For public bidding
20 | College of Fine Arts: New Building | Part of UP's Cultural Infrastructure Development Program (CIDP) | Enhanced learning environment | 100700000 |  |  | 2014 CO Budget (CIDP) | [6 empty] | 3 |  |  | In its pre-procurement stage (as of 11 May 2015)
21 | AIT: Tourism Heritage Complex | Major renovation, rehabilitation, retrofitting and modernization of the UP Asian Institute of Tourism complex | Enhanced learning environment | 90000000 |  |  | 2014 CO Budget (CIDP) | [6 empty] | 1 |  |  | For public bidding In its design stage (as of 11 May 2015)
22 | CMC: Virtual Arts & Culture Museum and Digital Media Archive | Construction of the Virtual Arts & Culture Museum and Digital Media Archive of the College of Mass Communication | Enhanced learning environment | 22400000 |  |  | 2014 CO Budget (CIDP) | [6 empty] | 1 |  |  | For public bidding - In its design stage (as of 11 May 2015)
23 | College of Music: Construction of Annex: Abelardo Hall Renovation | Construction of an annex building and renovation/ rehabilitation of the Abelardo Hall, College of Music | Enhanced learning environment | 53700000 |  |  | 2014 CO Budget (CIDP) | [6 empty] | 1 |  |  | For public bidding - In its design stage (as of 11 May 2015)
24 | College of Architecture Complex | Construction, renovation and rehabilitation of the College of Architecture buildings, facilities and surroundings | Enhanced learning environment | 200000000 |  |  | 2014 CO Budget | [6 empty] | 0 |  |  | For public bidding; pre-procurement conference: 02 Oct 2014
25 | Completion of the Industrial & Mechanical Engineering Building | Completion of the Industrial & Mechanical Engineering Building | Enhanced learning environment | 75000000 |  |  | 2014 CO Budget | [6 empty] | 0 |  |  | For public bidding
26 | Construction of the School of Statistics Building: Phase 2 | Completion of the new School of Statistics Building | Enhanced research environment and increased research productivity | 100000000 |  |  | 2015 CO Budget (NEP) | [6 empty] | 1 |  |  | Currently in its Schematic Plans/Design Phase Consultations being conducted with end users and among ODPI personnel Status updated as of 15 May 2015
27 | Construction of College of Home Economics Complex | Construction of College of Home Economics Complex | Enhanced learning environment | 150000000 |  |  | 2015 CO Budget (NEP) | [6 empty] | 1 |  |  | Preparation of first estimate for schematic plans/design (updated as of 11 May 2015)
28 | Construction of the Department of Computer Science Building | Construction of the Department of Computer Science Building | Enhanced learning environment | 110000000 |  |  | 2015 CO Budget (NEP) | [6 empty] | 1 |  |  | Preparation of first estimate for schematic plans/design (updated as of 11 May 2015)
29 | Construction of the College of Engineering Library (Phase II) | Construction of the College of Engineering Library | Improved access to academic support facilities and services for UP students | 60000000 |  |  | 2015 CO Budget (NEP) | [6 empty] | 1 |  |  | Preparation of first estimate for schematic plans/design (updated as of 11 May 2015)
30 | Completion of the Department of Mining, Metallurgical & Materials Engineering Building | Completion of the Department of Mining, Metallurgical & Materials Engineering Building | Enhanced learning environment | 70000000 |  |  | 2015 CO Budget (NEP) | [6 empty] | 1 |  |  | Preparation of first estimate for schematic plans/design (updated as of 11 May 2015)
31 | Completion of the Environmental Engineering Building | Completion of the Environmental Engineering Building | Enhanced learning environment | 4000000 |  |  | 2015 CO Budget (NEP) | [6 empty] | 1 |  |  | Preparation of first estimate for schematic plans/design (updated as of 11 May 2015)
32 | MSI Landscape Development | [12 empty] | 100 |  | 2011-10-10
33 | Supplementary Wing, Motorpool & Chemical Storage at NIGS Building |  |  | 20126165.54 | 18341640.34 |  | UPD RF | [6 empty] | 100 |  | 2013-07-14
34 | Rehabilitation Works at NIGS Building |  |  | 14105974.06 | 9456082.11 |  | UPD RF | [6 empty] | 100 |  | 2011-07-19
35 | Conversion of CSLAB to CSLIB at CS Administration Building |  |  | 21880564.74 | 21423366.07 |  | UPD RF | [6 empty] | 0 |  |  | Ongoing
36 | Institute of Chemistry Research Building Animal Room |  |  | 1300000 | 997668 |  | UPD RF | [6 empty] | 100 |  | 2012-02-15
37 | Landscaping Works at the CS Administration Building |  |  | 4500000 | 3142150 |  | UPD RF | [6 empty] | 0 |  |  | Ongoing
38 | National Science Complex Site Development Package 4 |  |  | 11000345.7 | 8249900.88 |  | UPD RF | [6 empty] | 100 |  | 2012-10-30
39 | National Science Complex Site Development Package 3 |  |  | 3216737.38 | 2571363.42 |  | UPD RF | [6 empty] | 100 |  | 2011-07-20
40 | Design & Build-NSC Site Development-Road Network Extension |  |  | 20000000 | 19868711.12 |  | UPD RF | [6 empty] | 0 |  |  | Ongoing
41 | Design & Build-National Center for Good Governance |  |  | 20000000 | 19392506.49 |  | UPD RF | [6 empty] | 0 |  |  | Ongoing
42 | Site Development of NSC-South Sector |  |  | 11521663 | 8648357.59 |  | UPD RF | [6 empty] | 100 |  | 2012-09-21
43 | Renovation of GE & ES Department at Melchor Hall |  |  | 26600000 | 20082680.88 | [8 empty] | 100 |  | 2013-09-20
44 | Construction of Department of Chemical Engineering Building |  |  | 123026000 | 105592267.03 | [8 empty] | 0 |  |  | Ongoing
45 | National Institute of Physics Renovation |  |  | 7500000 | 5029559.16 | [8 empty] | 0 |  |  | Unfinished by contractor
46 | Completion of Rehabilitation of BML Land-Based Hatchery, UP MSI Bolinao |  |  | 5844075.57 | 4701751.62 |  | UPD RF | [6 empty] | 100 |  | 2012-03-28
47 | MSI Lab Animal Facility & MSI Chemical Wastehouse |  |  | 2423453.28 | 2052354 |  | UPD RF | [6 empty] | 100 |  | 2013-03-24
48 | Provision of Additional Spaces, Fire Safety Measures & Cold Storage at MSI |  |  | 8675000 | 8584660.88 |  | UPD RF | [6 empty] | 0 |  |  | Ongoing
49 | Renovation Works at NSRI |  |  | 17413979.49 | 11376256.65 | [8 empty] | 0 |  |  | Ongoing
50 | College of Science Administration Building & Site Development |  |  | 142478683.06 | 119455853.69 | [8 empty] | 0 |  |  | Ongoing
51 | Kamagong Centennial Dorm 1-Portion of Perimeter Fencing, Gateway & Parking |  |  | 1959368.97 | 1783257.87 |  | TFI | [6 empty] | 100 |  | 2011-06-02
52 | Additional Security Fence at International Center & Ilang-Ilang Residence Hall |  |  | 473818.76 | 469995 |  | TFI | [6 empty] | 100 |  | 2011-08-12
53 | Renovation Works-Math Building |  |  | 9675931.26 | 5850995 | [8 empty] | 100 |  | 2011-08-18
54 | Renovation of VCSA Office at Ground Floor, QH |  |  | 868647.46 | 848995 |  | UPD RF | [6 empty] | 100 |  | 2011-07-08
55 | Re-Waterproofing of Math Building Roof Deck, RC Gutters & Parapets |  |  | 2482903.46 | 1832391.78 |  | UPD RF | [6 empty] | 100 |  | 2012-06-30
56 | Design & Build-Acacia Residence Hall & Law Centennial Dormitory |  |  | 205233756.48 | 180025600.93 | [8 empty] | 0 |  |  | Ongoing
57 | Land Development & Other Facilities-Engineering Library & Computer Science Building |  |  | 615459.84 | 556246.3 | [8 empty] | 100 |  | 2011-07-16
58 | Renovation of Corridor Gallery & Digital Media Expansion, College of Fine Arts |  |  | 600440.63 | 510327.44 |  | UPD RF | [6 empty] | 100 |  | 2011-06-15
59 | Re-roofing & Ceiling Rehabilitation Works-Sampaguita Residence Hall |  |  | 2791140.74 | 2050980 | [8 empty] | 100 |  | 2011-07-30
60 | Re-roofing & Miscellaneous Works-NIML Building, CHE |  |  | 665674.09 | 644098.25 | [8 empty] | 100 |  | 2011-11-13
61 | Repair of Roof Gutter-SURP |  |  | 722470.78 | 598759.39 |  | UPD RF | [6 empty] | 100 |  | 2012-01-03
62 | Renovation of Palma Hall 104-106-Department of Geography, CSSP |  |  | 532610.49 | 464335.31 |  | UPD RF | [6 empty] | 100 |  | 2011-12-05
63 | Interior Repainting of College of Engineering Library 1-Melchor Hall |  |  | 292879.21 | 247198.4 | [8 empty] | 100 |  | 2011-12-15
64 | Additional Stamped Concrete Slabs for Alumni Walk-Academic Oval |  |  |  | 100520 | [8 empty] | 100 |  | 2011-11-16
65 | Repair of Theater Roof |  |  | 379962.06 | 289564.2 |  | UPD RF | [6 empty] | 100 |  | 2011-12-13
66 | Upgrading of Electrical System of Gonzalez Hall |  |  |  | 3400123.86 |  | UPD RF | [6 empty] | 0 |  |  | Ongoing
67 | Renovation of Ipil Residence Hall |  |  | 14996834.68 | 11745078.07 |  | TFI | [6 empty] | 100 |  | 2013-03-26
68 | Rewiring/Upgrading of Electrical System at NIGS Building |  |  | 5940000 | 3292571.6 | [8 empty] | 100 |  | 2012-01-18
69 | Renovation of Balay Chancellor |  |  | 499588 | 414871.16 |  | UPD RF | [6 empty] | 100 |  | 2012-01-06
70 | Cleaning and Repainting of Ceiling, Steel Handrails, Steel Trusses & Walls-CSWCD |  |  | 305950.51 | 288770 |  | UPD RF | [6 empty] | 100 |  | 2011-10-10
71 | Panel Boards for Existing & Future Loads-Bocobo Hall, College of Law |  |  | 938403.42 | 900947 |  | UPD RF | [6 empty] | 100 |  | 2011-09-30
72 | Renovation & Miscellaneous Works Phase 3-UP Health Service |  |  | 4006151.53 | 3151631.34 |  | UPD RF | [6 empty] | 100 |  | 2011-12-02
73 | Trenching for DILNET |  |  | 4996132.1 | 4086635.61 |  | UPD RF | [6 empty] | 100 |  | 2011-10-03
74 | Re-roofing & Miscellaneous Works-CHK |  |  | 6828732.88 | 4730045.21 |  | UPD RF | [6 empty] | 100 |  | 2011-12-19
75 | Energy & Environmental Engineering Building Phase 2 |  |  | 145484095.49 | 116816836.68 | [8 empty] | 0 |  |  | Ongoing
76 | Replacement of Lighting Fixtures-CHK Gym |  |  | 1034157.81 | 852078.58 |  | UPD RF | [6 empty] | 100 |  | 2012-03-28
77 | Re-Piping of Fresh Water Main Line & Miscellaneous Works-UP MSI Bolinao |  |  |  | 1696315.89 |  | UPD RF | [6 empty] | 100 |  | 2012-10-17
78 | Renovation of 3rd Floor Toilets-TBI, NEC |  |  | 379092.74 | 368355.93 |  | UPD RF | [6 empty] | 100 |  | 2012-08-06
79 | Various Renovation Works-UP MSI Bolinao |  |  | 4156146.8 | 3424496.15 |  | UPD RF | [6 empty] | 100 |  | 2012-11-16
80 | Malcolm Hall Frontage Landscape Development-Retaining Wall, Canopy & Grass |  |  | 697277.33 | 635786.6 | [8 empty] | 100 |  | 2011-04-15
81 | Philippine Collegian Office Renovation-Vinzons Hall |  |  | 969804.92 | 820480.17 | [8 empty] | 100 |  | 2012-04-14
82 | Completion of CMC Film Media Center Building-College of Mass Communication |  |  | 9900900.1 | 8600000 | [8 empty] | 0 |  |  | Unfinished by contractor
83 | Renovation of Graduate Studies Department-Plaridel Hall Annex CMC |  |  | 769891.12 | 674017.28 |  | UPD RF | [6 empty] | 100 |  | 2012-06-07
84 | Renovation of the Office of the Dorm Manager-Sampaguita Residence Hall |  |  | 368687.34 | 360910.48 |  | TFI | [6 empty] | 100 |  | 2012-04-05
85 | Plaridel Hall Basement Renovation-CMC |  |  | 872048.61 | 871822.05 |  | UPD RF | [6 empty] | 100 |  | 2012-06-18
86 | Renovation of Accounting, Budget, Cashiers & VC for Finance Office-PNB Building |  |  | 10529585.81 | 9023571.54 | [8 empty] | 100 |  | 2013-08-02
87 | Store Room-College of Music |  |  | 218434.64 | 205484.57 |  | UPD RF | [6 empty] | 100 |  | 2012-07-04
88 | Housing Office Renovation-CMO |  |  | 619464.55 | 529152.11 |  | UPD RF | [6 empty] | 100 |  | 2012-06-26
89 | Renovation of Fire-Damaged HRDO Administration Office-Ground Floor QH |  |  | 975585 | 818458.28 |  | UPD RF | [6 empty] | 100 |  | 2012-09-26
90 | Repainting of QH Exteriors Phase 1 |  |  | 488667.64 | 412450.23 | [8 empty] | 100 |  | 2012-06-04
91 | Centennial Dormitory Building 2 (Phase2) & Site Development at Kamagong Centennial Dormitories |  |  | 22467219.93 | 18229695.07 | [8 empty] | 100 |  | 2014-03-07
92 | Waterproofing of STTC Roofdeck-NISMED |  |  | 3486355.2 | 2611384 | [8 empty] | 100 |  | 2013-01-28
93 | Renovation of Rooms 312-316 NEC |  |  | 7774825.53 | 6088722.97 | [8 empty] | 0 |  |  | Ongoing
94 | Renovation of Toilets & Miscellaneous Works-Abelardo Hall |  |  | 3925601.08 | 3491978.69 | [8 empty] | 100 |  | 2013-01-12
95 | Diliman Information Office-University Theater |  |  | 300000 | 253122.86 |  | UPD RF | [6 empty] | 100 |  | 2013-04-09
96 | Repainting & Miscellaneous Works-Sampaguita Residence Hall |  |  | 174573.59 | 162807.21 | [8 empty] | 100 |  | 2012-12-01
97 | Philippine Genome Center-NIMBB Building |  |  | 291233.44 | 289100.21 | [8 empty] | 100 |  | 2013-04-19
98 | Construction of Bridge & Amphitheater-College of Architecture |  |  | 6207500.97 | 5793012.52 | [8 empty] | 0 |  |  | Ongoing
99 | Storm Drainage |  |  | 489414.88 | 428432.29 |  | UPD RF | [6 empty] | 100 |  | 2013-04-05
100 | Re-roofing & Miscellaneous Works-Alimni Dormitory |  |  | 1377634.05 | 995905.36 | [8 empty] | 0 |  |  | Ongoing
101 | Renovation of Diliman Legal Office |  |  | 2273674.66 | 1907856.68 |  | UPD RF | [6 empty] | 100 |  | 2013-02-05
102 | Re-roofing & Miscellaneous Works-Espititu Hall, UP Law Center |  |  | 1591579.43 | 1304440.71 |  | UPD RF | [6 empty] | 100 |  | 2013-01-12
103 | Storm Drainage System |  |  |  | 350608.1 |  | UPD RF | [6 empty] | 100 |  | 2013-04-09
104 | Rerouting & Rewiring-Vargas Museum |  |  |  | 945000 | [8 empty] | 100 |  | 2013-02-07
105 | Re-roofing & Miscellaneous Works-PARDEC Building NCPAG |  |  | 2461023.14 | 1622349.6 | [8 empty] | 100 |  | 2013-06-12
106 | Academic Building 1 Phase 2-UPEPP |  |  |  | 23261246.19 | [8 empty] | 0 |  |  | Ongoing
107 | Classroom Building 1 Phase 2-UPEPP |  |  |  | 6520775.14 | [8 empty] | 0 |  |  | Ongoing
108 | Expansion of CHK Library |  |  | 242655.3 | 241221.1 | [8 empty] | 100 |  | 2013-05-15
109 | Renovation of Classroom 124-Palma Hall CSSP |  |  | 138244.86 | 125323.16 |  |  | Ravilo-Gonzales Group Construction Corporation | [5 empty] | 100 |  | 2013-05-08
110 | Repainting of Walls & Waterproofing of Canopy-NCPAG |  |  | 361498.99 | 312787.8 |  |  | Reygem Builders | [5 empty] | 100 |  | 2014-10-02
111 | Renovation of NISMED Auditorium |  |  | 438170.39 | 394349.6 |  |  | Reygem Builders | [5 empty] | 100 |  | 2013-08-31
112 | Re-waterproofing of Roof Slab-MSI |  |  | 363119.12 | 289275 |  |  | Reygem Builders | [5 empty] | 100 |  | 2013-06-27
113 | Signage for NIMBB Building-NSC Complex |  |  | 166520.35 | 165912.74 |  |  | Ravilo-Gonzales Group Construction Corporation | [5 empty] | 100 |  | 2014-02-13
114 | Re-roofing of Bocobo Hall-Law Center |  |  | 2002230.82 | 1754524.7 |  |  | M.P. Villegas Construction | [5 empty] | 100 |  | 2014-10-02
115 | Renovation of Office of Community Relations |  |  | 332865.28 | 300124.57 |  | UPD RF | Reygem Builders | [5 empty] | 100 |  | 2014-02-24
116 | Landscape Development-CMC Courtyard |  |  | 795407.02 | 700214.81 |  |  | Reygem Builders | [5 empty] | 100 |  | 2014-02-12
117 | NSC Site Development-Buildings & Open Spaces |  |  | 4644069.47 | 3866186.32 | [8 empty] | 100 |  | 2014-10-02 | For punchlisting
118 | Completion of CHK Multi-Purpose Building |  |  | 596732.05 | 524880.5 |  |  | PGM Construction and Plumbing Services | [5 empty] | 100 |  | 2014-02-17
119 | Extension of Accounting Office & Miscellaneous Works |  |  | 671200 | 671200.44 |  |  | Reygem Builders | [5 empty] | 100 |  | 2014-03-19 | Negotiated procurement
120 | Rehabilitation of MSI Attic & Stock Rooms |  |  | 595713.32 | 500000 |  | UPD RF | Reygem Builders | [5 empty] | 100 |  | 2014-03-14
121 | Renovation of Plaridel Hall Basement |  |  | 111150 | 111150 |  | UPD RF | Reygem Builders | [5 empty] | 100 |  | 2013-12-10
122 | Repainting of OUR Building Roof |  |  | 122330.1 | 110231.91 |  | UPD RF | PGM Construction and Plumbing Services | [5 empty] | 100 |  | 2014-01-15
123 | Renovation of NEC Building Basement |  |  | 1456310.68 | 1235628.79 |  | UPD RF | M.P. Villegas Construction | [5 empty] | 90 |  |  | Ongoing
124 | Renovation of CHK Faculty Restrooms |  |  | 262655.76 | 243478.17 |  |  | Ravilo-Gonzales Group Construction Corporation | [5 empty] | 100 |  | 2014-05-06
125 | Renovation of Kapit Balay Walk-Up Housing |  |  | 1822965.41 | 1200133.77 |  |  | Reygem Builders | [5 empty] | 100 |  | 2014-10-02
126 | Diliman Information Office Phase 2 |  |  | 384547.54 | 344604.98 |  | UPD RF | Ravilo-Gonzales Group Construction Corporation | [5 empty] | 90 |  |  | Ongoing
127 | Repainting of GT Toyota Hall of Wisdom & Asian Center Auditorium |  |  | 586719.95 | 499816 |  |  | Ercobal Construction Corporation | [5 empty] | 100 |  | 2014-04-10
128 | UP Moog Security Grilles |  |  | 120733.65 | 99878.49 |  |  | PGM Construction and Plumbing Services | [5 empty] | 100 |  | 2014-10-02
129 | Upgrading/Rewiring of Data Systems, VSB |  |  | 3064885.29 | 3058252.96 |  |  | NVSP Construction and Development | [5 empty] | 0 |  |  | Ongoing
130 | Renovation of OVCRD Auditorium & Central Files Room |  |  | 816267.94 | 720373.45 |  | UPD RF | PGM Construction and Plumbing Services | [5 empty] | 0 |  |  | Ongoing; with variation order
131 | CSSP East Covered Walkway, Palma Hall |  |  | 1913875.6 | 1474076.18 |  |  | Reygem Builders | [5 empty] | 100 |  | 2014-10-02
132 | Re-roofing of Library, College of Home Economics |  |  | 787563.86 | 671856.6 |  |  | Reygem Builders | [5 empty] | 100 |  | 2014-10-02
133 | Modification of Electrical Service Entrance, Accounting, Budget & Cashier's Office |  |  | 217849.04 | 135990.4 |  | UPD RF | Reygem Builders | [5 empty] | 100 |  | 2014-05-14
134 | Re-roofing & Miscellaneous Works-Albert Hall |  |  | 2427184.43 | 1914218.21 |  | UPD 60% Share of Technohub/UP Town Center | Reygem Builders | [5 empty] | 0 |  |  | Ongoing
135 | Free Standing Drug Testing Screening Lab, University Health Service |  |  | 1591179.87 | 1569400.28 |  | UPD RF | Enrivel Construction | [5 empty] | 0 |  |  | Ongoing
136 | Trenching for DILNET, CFA Communication Manhole to Centennial Dorm |  |  | 2792916.61 | 2647993.86 |  |  | M.P. Villegas Construction | [5 empty] | 0 |  |  | Ongoing
137 | Replacement of Walkway and Pavement at Gonzalez Hall |  |  | 5067379.52 | [9 empty] | 0 |  |  | Award on hold; post-disqualification issue
138 | Creek Security Barrier, NSC |  |  | 197737.81 | 194927.04 |  | UPD RF | PGM Construction and Plumbing Services | [5 empty] | 0 |  |  | Ongoing
139 | Renovation of 3rd Floor Office at BOCOBO Hall |  |  | 7139672.29 | 5701603.94 | [8 empty] | 0 | 2014-11-05 |  | Ongoing
140 | Re-roofing & Miscellaneous Works-Hardin ng Rosas |  |  | 19417475.73 | 15588997.76 |  |  | Accuracy Builder Enterprise | [5 empty] | 0 | 2014-11-05 |  | Ongoing
141 | Storm Drainage at the Washington Sycip Garden of Native Trees |  |  | 350608.1 | 350608.1 |  |  | M.P. Villegas Construction | [5 empty] | 100 |  | 2014-10-02
142 | Extension of University Hotel Patio |  |  | 1616532.23 | 1148811.31 |  |  | Enrivel Construction | [5 empty] | 100 | 2014-10-02
143 | Design & Build-Fencing and Site Development (Engineering Complex) |  |  | 23923444.98 | [9 empty] | 0 |  |  | Bidding postponed indefinitely
144 | CSSP Rizal Garden, Storm Drainage Rehabilitation and Covered Walkway, Palma Hall |  |  | 1099730.93 | 980775.43 |  |  | Reygem Builders | [5 empty] | 0 |  |  | Awarded; contract preparation
145 | Construction of Generator House & Miscellaneous Works, MSI |  |  | 513650.25 | [9 empty] | 0 |  |  | Bid evaluation as of 18 Sep 2014
146 | Renovation of Plaridel Hall Frontage, Repainting & Waterproofing Works, CMC |  |  | 3062200.95 | [9 empty] | 0 |  |  | Bidding; closing date: 23 Oct 2014
147 | Budget Office Site Development & Storage Room |  |  | 535210.19 | [9 empty] | 0 |  |  | Bidding; closing date: 16 Oct 2014
148 | Retaining Wall-Kamia Residence Hall Parking Area |  |  | 170746.48 |  |  | TFI | [6 empty] | 0 |  |  | Bidding; closing date: 02 Oct 2014
149 | Rehabilitation of CHE Craft Design, Clothing Technology & Interior Design Labs |  |  | 485086.15 |  |  | UP System RF | [6 empty] | 0 |  |  | Failed bidding; no bidders
150 | Reinforced Concrete Counter with Stainless Steel Sinks & Plumbing Works-UPIS |  |  | 337770.27 | [9 empty] | 0 |  |  | Bid evaluation as of 18 Sep 2014
151 | Repair of Gym Roof Vent & Miscellaneous Works, Main Gym, CHK |  |  | 405271.57 |  |  | UPD RF | [6 empty] | 0 |  |  | Bid evaluation as of 18 Sep 2014
152 | Waterline Re-piping of UP ISSI Building |  |  | 557242.4 | [9 empty] | 0 |  |  | Bid evaluation as of 18 Sep 2014
153 | Renovation of Bocobo Lecture Hall, College of Law |  |  | 2737308.39 | 2027419.17 |  |  | Reygem Builders | [5 empty] | 0 |  |  | Awarded; contract preparation
154 | College of Law Employees' Canteen, Malcolm Hall |  |  | 1254626.14 | [9 empty] | 0 |  |  | Failed bidding; no bidders
155 | Renovation of Communication Research Room, Plaridel Hall, CMC |  |  | 2392344.47 | 2156958.03 |  |  | Jesus Asuncion Builders | [5 empty] | 0 |  |  | Contract preparation
156 | Replacement of Existing Garage Concrete Wall, NEC |  |  | 194735.33 | 194735.33 |  |  | M.P. Villegas Construction | [5 empty] | 0 |  |  | Ongoing
157 | New SURP Building |  |  | 145000000 |  |  | UP System RF (Proposed) | [6 empty] | 0 |  |  | ODPI to coordinate with OCA in finalizing plans & project specs
158 | College of Music Building (on top of Funding under CIDP) |  |  | 145000000 |  |  | UP System RF (Proposed) | [6 empty] | 0 |  |  | ODPI to coordinate with OCA in finalizing plans & project specs
159 | Re-roofing of Hardin ng Rosas | [12 empty] | 0 |  |  | For awarding as of 01 Sep 2014
160 | Replacement of Gonzales Hall (University Library) Existing Walkway and Pavement | [12 empty] | 0 |  |  | For awarding as of 01 Sep 2014
161 | Bocobo Hall Lecture Room | [12 empty] | 0 |  |  | For awarding as of 01 Sep 2014
162 | Construction of UPIS 3-6 Canteen and Renovation of 7-12 Canteen | [12 empty] | 0 |  |  | For public bidding
163 | Renovation of Ipil Residence Hall-Phase 3 | [12 empty] | 0 |  |  | For public bidding
164 | Repair of UP Gym Vent | [12 empty] | 0 |  |  | For public bidding
165 | Re-piping of Hardin ng Doña Aurora (UP Housing Office) | [12 empty] | 0 |  |  | For public bidding
166 | Re-piping of Hardin ng Rosas (UP Housing Office) | [12 empty] | 0 |  |  | For funding
167 | Renovation of CSSP Pavilion 4 | [12 empty] | 0 |  |  | For funding
168 | MSI Seaweed Building Renovation/Rewiring | [12 empty] | 0 |  |  | For funding
169 | Rewiring of MSI Building | [12 empty] | 0 |  |  | For funding
170 | Generator for MSI Building | [12 empty] | 0 |  |  | For funding
171 | Construction of Bridge/Walkway at NCPAG | [12 empty] | 0 |  |  | Surveying of site/preliminary investigation
172 | Renovation of UPIS Bulwagan | [12 empty] | 0 |  |  | Surveying of site/preliminary investigation
173 | Re-packaging of Terminated Contract for NCPAG | [12 empty] | 0 |  |  | Assessment of Unfinished Building
174 | Re-roofing of Kalayaan Residence Hall | [12 empty] | 0 |  |  | For design
175 | Renovation of Kitchen and Dining Area of Ilang-Ilang Residence Hall | [12 empty] | 0 |  |  | For deisgn
176 | Air-con Sheds at NISMED/STTC Roofdeck | [12 empty] | 0 |  |  | For design
177 | Re-roofing of CSWCD Building | [12 empty] | 0 |  |  | For design
178 | Elevator/Elevator Shaft for ICTO Building | [12 empty] | 0 |  |  | For design
179 | DILNET Trenching for IESM Building | [12 empty] | 0 |  |  | For design
180 | DILNET Trenching for NIP Building | [12 empty] | 0 |  |  | For design
181 | College of Fine Arts Annex Building | [12 empty] | 0 |  |  | For design
182 | TMC Outdoor Lighting | [12 empty] | 0 |  |  | For design and cost estimate
183 | Electrical Upgrading of Yakal Residence Hall | [12 empty] | 0 |  |  | For design and cost estimate
184 | Faculty & Staff Housing-Phase 1 | Construction of three (3) new housing buildings in response to the growing demand from UP Diliman faculty and staff for on-campus housing | Improved access to on-campus housing for UP faculty & staff; increased productivity | 197999690 | 192635427 |  | 2012 CHED Funding | C.E. Padilla Construction Inc. | 3 | 2014-01-17 | 2014-10-07 |  |  | 15 |  |  | Project has been formally turned over from UP System to UP Diliman as of 18 March 2015. OVPD / ODPI shall continue to assist in facilitating the transition and execution of the project.
185 | Faculty & Staff Housing-Phase 2 |  |  | 300000000 | [9 empty] | 0
44 | Renovation of Ilang-Ilang Residence Hall |  |  | 13471607 | 10641443 |  | 2012 CHED Funding | Enrivel Construction | [5 empty] | 100 |  | 2014-04-24 | Completed as of 24 Apr 2014
44 | Renovation of Ipil Residence Hall |  |  | 3364078 | 2601234 |  | 2012 CHED Funding | Enrivel Construction | [5 empty] | 100 |  | 2013-11-27 | Completed as of 27 Nov 2013
44 | Renovation of Sampaguita Residence Hall |  |  | 4805825 | 3807485 |  | 2012 CHED Funding | MP Villegas Construction | [5 empty] | 100 |  | 2015-03-24 | - Awaiting permanent power connection
44 | Reroofing & Miscellaneous Works-Molave Residence Hall |  |  | 5569101 | 3125047 |  | 2012 CHED Funding | Mechanics Construction Corporation | [5 empty] | 50 |  |  | - Works suspended - Cannot proceed pending variation order #1
44 | Re-piping & Miscellaneous Works-Kamagong Residence Hall |  |  | 2514640 | 1729875 |  | 2012 CHED Funding | Three W Builders |  |  | 2013-07-08 |  |  | 100 |  | 2014-10-31 | Original contract completed as of 31 Oct 2014; with variation order
44 | Renovation of Toilets & Miscellaneous Works-Kalayaan Residence Hall |  |  | 10873786 | 9377673 |  | 2012 CHED Funding | Eastern Construction | [5 empty] | 100 |  | 2015-04-22 | Completed as of 22 Apr 2015
44 | Renovation of Toilets & Miscellaneous Works-Sanggumay Residence Hall |  |  | 2912621 | 2457228 |  | 2012 CHED Funding | Mechanics Construction Corporation |  |  | 2013-06-14 |  |  | 100 |  | 2014-04-18 | Completed as of 18 Apr 2014
44 | Renovation of Yakal Residence Hall |  |  | 8249915 | 5759759 |  | 2012 CHED Funding | Reygem Builders |  |  | 2013-07-29 |  |  | 100 |  | 2015-01-14 | Completed as of 14 Jan 2015
44 | Renovation of Rooms & Miscellaneous Works-Kamia Residence Hall |  |  | 1922330 | 1574851 |  | 2012 CHED Funding | MP Villegas Construction | [5 empty] | 100 |  | 2014-01-24 | Completed as of 24 Jan 2014
47 | Site Development for NSC Buildings and Open Areas |  |  | 4644069 | 3866193 |  | 2012 CHED Funding | Jesus Asuncion Builders | [5 empty] | 100 |  | 2014-05-05 | Completed as of 05 May 2014
47 | Replacement of Retaining Wall & Miscellaneous Works-NSRI | Construction/rehabillitation of the National Science Complex immediate vicinity/premises | Enhanced learning/research environment and increased research productivity | 1986723 | 1986723 |  | 2012 CHED Funding | Accuracy Builders |  |  | 2013-01-29 |  |  | 100 |  | 2013-12-06 | completed as of 06 Dec 2013
47 | Manila Water Connection for NSC Buildings |  |  | 800000 |  |  | 2012 CHED Funding | [6 empty] | 100 |  | 2014-05-05 | Completed as of 05 May 2014
50 | Renovation of Palma Hall Building Package 2 (CAL)-Palma Hall Pavilions 1&3 |  |  | 19142968 | 19142968 |  | 2012 CHED Funding | Alleyway Construction | [5 empty] | 90 | 2015-05-31 |  | - Work suspended due to pending negotiated contract for roofing works
50 | Renovation of Palma Hall Building Package 1 (CSSP)-Palma Hall Pavilions 1,2&4 |  |  | 38547706 | 38547706.24 |  | 2012 CHED Funding | Alleyway Construction | [5 empty] | 70 | 2015-05-01 |  | Ongoing
Note on E16: 49,500,000 according to COA