## UP LOS BAÑOS
INFRASTRUCTURE PROJECTS
OCTOBER 2014
UP LOS BAÑOS | [13 empty] | 100
| PROJECT | PROJECT DESCRIPTION | DESIRED PROJECT OUTCOME | BUDGET (PhP) | CONTRACT PRICE (PhP) | ACTUAL COST (PhP) | SOURCE OF FUNDS | Contractor/Vendor | No. of Biddings | Date of Notice of Award | Date of Notice to Proceed | TARGET START DATE | ACTUAL START DATE | % ACCOMPLISHMENT | TARGET COMPLETION DATE | ACTUAL COMPLETION DATE | REMARKS (Problems/Issues Encountered and Other Pertinent Information Regarding the Project) | PROGRESS BILLING 1 | PROGRESS BILLING 2 | PROGRESS BILLING 3 | PROGRESS BILLING 4 | PROGRESS BILLING 5 | PROGRESS BILLING 6 | PROGRESS BILLING 7 | PROGRESS BILLING 8 | PROGRESS BILLING 9 | PROGRESS BILLING 10
1 | UPLB IASL Laboratory Equipment | Acquisition of laboratory equipment for the UPLB Integrated Analytical Services Laboratory (IASL) | Enhanced research environment and increased research productivity | 48210000 | 11700000 |  | 2012 CHED Funding | Various suppliers | [5 empty] | 100 |  | 2014-10-02 | Has not been rebid
2 | UPLB IASL Building |  |  | 30000000 |  |  | 2012 CHED Funding | [6 empty] | 0 |  |  | Two failed biddings; has not been rebid
3 | eUP Component 4: ICT Infra Development: Strengthening Campus Security & Safety | Procurement of various ICT hardware/equipment, perpherals and other related devices to enhance security and safety in the UPLB campus | Improved campus security & safety | 26500000 | 21950000 |  | 2013 CO Budget | Multi-fold Links Incorporated |  |  |  |  | 2014-02-10 | 61.45 |  |  | - 28.95% slippage as of 01 Sep 2014 - Contract has been terminated on 29 Sep 2014 due to fundamental breach and/or unlawful acts
4 | eUP Component 4: ICT Infra Development: Philippine Tropical Forest Science Center | Procurement of various ICT hardware/equipment, peripherals, specifically for the Philippine Tropical Forest Science Center | Enhanced research environment and increased research productivity | 15000000 | 12766893.85 |  | 2013 CO Budget | [5 empty] | 2014-02-11 | 21.5 |  |  | - contract time suspended on 14 Mar 2015 because of discrepancies found on actual elevations with reference to the issued plans which CPDO finds critical during construction - proposed variation order/change order and time extension of 20 calendar days was approved on 13 Oct 2014 - contract time suspension was lifted on 20 Oct 2014 - Permit to cut trees through the Jose Velasco Road has not been issued by DPWH (only affecting PRIORITY 1) - Status updated as of 11 May 2015
5 | Development of Art Spaces | Further renovation and rehabilitation of the DL Umali Hall, which houses the auditorium and the Sining Makiling Gallery | Enhanced learning environment | 9400000 |  |  | 2014 CO Budget (CIDP) | [6 empty] | 5 |  |  | - Architectural and sanitary/plumbing design completed - preparation of estimate ongoing - electrical and mechanical design ongoing - Status updated as of 11 May 2015
6 | Makiling Film Lab | Construction of the Makiling Film Lab to promote film appreciation and literacy | Enhanced learning/research environment and increased research productivity | 6743000 |  |  | 2014 CO Budget (CIDP) | [6 empty] | 5 |  |  | - Architectural plan and estimate completed - Estimate for correction - Engineering design ongoing - Status updated as of 11 May 2015
7 | Establishment of the Graduate School International Student and Cultural Center | Establishment of the Graduate School International Student and Cultural Center | Improved access to academic support facilities and services for UP students, faculty & staff | 71800000 |  |  | 2014 CO Budget | [6 empty] | 0 |  |  | TOR completed - Bidding for A&E Design Services ongoing - Status updated as of 11 May 2015
8 | Construction of the Philippine Tropical Forest Science Center-Phase 2 | Construction of the Philippine Tropical Forest Science Center-Phase 2 | Enhanced research environment and increased research productivity | 32000000 |  |  | 2015 CO Budget (NEP) | [6 empty] | 0 |  |  | Construction ongoing - Status updated as of 11 May 2015
9 | Acquisition of Various Equipment for the Philippine Tropical Forest Science Center-Phase 2 | Acquisition of Various Equipment for the Philippine Tropical Forest Science Center-Phase 2 | Enhanced learning/research environment and increased research productivity | 27000000 |  |  | 2015 CO Budget (NEP-EO) | [6 empty] | 0
10 | Construction of the University Health Service Extension Building (Proposed extension will not be pursued since a new building will be constructed) | Construction of the University Health Service Extension Building | Improved access to academic support facilities and services for UP students, faculty & staff | 40000000 |  |  | 2015 CO Budget (NEP) | [6 empty] | 0 |  |  | Site for expansion identified by AVP Espina TOR template to be provided by ODPI Design Development Plan preparation ongoing Status updated as of 19 May 2015
11 | College of Economics & Management 4-Storey Building | Renovation/rehabilitation of the College of Economics and Management building in UPLB | Enhanced learning environment | 90000000 |  |  | UP System RF (Proposed) | [6 empty] | 0 |  |  | TOR preparation is finished.
12 | Rehabilitation of National Plant Genetic Resources Lab (NPGRL) Building, IPB Compound | Reconstruction of National Plant Genetic Resources Laboratory Building | Enhanced learning/research environment and increased research productivity |  | 2902934 | [8 empty] | 100 |  | 2011-11-28
13 | Rehabilitation of Various CA Buildings and Facilities |  |  |  | 3101811 |  | UPLB GF | [6 empty] | 100 |  | 2012-02-16
14 | Construction of Two-Storey IT Building (Formerly 2-Storey Library); Completion of Electrical Works and Storm Drain System, UP Rural High School |  |  |  | 1752440 |  | UPLB RF | [6 empty] | 100 |  | 2012-06-09
15 | Rehabilitation of CAS Buildings and Facilities |  |  |  | 9424689 |  | UPLB GF | [6 empty] | 100 |  |  | Completed as of 31 Aug 2012
16 | Construction of CE Annex Building, CEAT |  |  |  | 2390922 |  | UPLB RF | [6 empty] | 100 |  |  | Completed as of 02 Dec 2013
17 | Construction of Rural Economic Development and Renewable Energy Center (REDREC), Phase 1, CEM Compound |  |  |  | 15326433 |  | UPLB GF | [6 empty] | 100 |  |  | Completed as of 29 Jun 2013
18 | Construction of Junior Faculty Room, Phase 1, 2nd Floor, Molecular Biology and Biotechnology Building, IBS |  |  |  | 3881137 |  | UPLB RF | [6 empty] | 100 |  |  | Completed as of 16 Aug 2013
19 | Rehabilitation of CA Agri-Park Multi-Purpose Hall |  |  |  | 1951519 |  | DA Funding | [6 empty] | 100 |  |  | Completed as of 17 Dec 2013
20 | Construction of Classrooms, Industrial Engineering Building, CEAT |  |  |  | 2353821 |  | UPLB RF | [6 empty] | 100 |  |  | Completed as of 24 Jan 2014
21 | Repair and Rehabilitation of Annex Laboratory Building, Phase 2, Department of Forest Products and Paper Science (DFPPS), CFNR |  |  |  | 1886712 | [8 empty] | 16 |  |  | 16% complete as of 15 Jul 2013 work suspended since 15 Jul 2013 pending PVO#1 documentation (contractor to submit breakdown of estimates) follow up letter sent on 01 Jan 2014, but no response from contractor as of 30 Sep 2014 As of 19 May 2015, remaining works include installation of roofing sheets and ceiling, and interior finishing
22 | Construction of UPLB Gym (Completion of Phase 5, Wing B) |  |  |  | 16848478.92 | [7 empty] | 2013-11-18 | 100 |  | 2015-05-11 | - 65.88% complete as of 16 Sep 2014; - project recommended for termination on 20 Jun 2014; - contract time extension of 17 calendar days approved by the Chancellor on 30 Jan 2015 Completed as of 11 May 2015 and for rectification of punchlisting
23 | Construction of UPLB Gym Driveway and Parking Lot |  |  |  | 10644218.26 | [7 empty] | 2013-11-09 | 31.32 |  |  | Contract was terminated on 11 Jul 2014; notice of termination sent to contractor on 21 Jul 2014; contractor has submitted appeal to OC on 28 Aug 2014; 31.32% complete as of 08 Aug 2014 UPLB is still waitinf for the notice from the Construction Industry Arbitration Committee (CIAC) - Status updated as of 19 May 2015
24 | Construction of 3-Storey Math Building |  |  |  | 52571641.7 | [7 empty] | 2014-01-20 | 35.29 |  |  | - Ongoing - 30.48% complete as of 16 Sep 2014 - project has been recommended for termination on 20 Jun 2104
25 | Tennis Courts |  |  |  | 4000000 | [8 empty] | 0 |  |  | Purchase request already signed bythe Chancellor
26 | Bicycle Lane (Pili Drive to IRRI) |  |  |  | for negotiation with IRRI re fund requirement | [8 empty] | 0 |  |  | revision of design and cost estimate completed
27 | Construction of New Dormitory |  |  |  | 60000000 |  | TFI | [6 empty] | 0 |  |  | revision of architectural and engineering plans is ongoing
28 | Construction of e-Library, Interactive Learning Center (ILC) and IT Center (ITC) Beside UPLB Main Library (Global Academic Zone) |  |  |  | no funding yet | [8 empty] | 0 |  |  | Preparation of TOR is completed
29 | Rehabilitation and Recommissioning of Existing UPLB Sewage Treatment Plant |  |  |  | 20000000 | [8 empty] | 0 |  |  | Draft TOR for refinement (design and build scheme)
30 | Institute of Agriculture Engineering, Agricultural and Bio-Processing Division (IAE-ABPROD) |  |  |  | 22000000 | [8 empty] | 0 |  |  | Bidding for design services is ongoing
31 | Centralized Communal Classroom Building (Lecture Halls/Lab Rooms), Math Building Compound | [12 empty] | 0 |  |  | preparation of TOR is ongoing
32 | Knowledge Center for Agriculture, Forestry and Environment, CFNR Training and Extension Office (Baguio City) | [12 empty] | 0 |  |  | Waiting for formal turnover of the property by the BFD-DENR to UPLB
33 | Men's Dormitory Building (Unit 1), Waling-Waling Road |  |  |  | not funding yet | [8 empty] | 0 |  |  | For preparation of TOR
34 | Construction of 3-Storey University Health Service Building |  |  |  | 40000000 | [8 empty] | 0 |  |  | For preparation of TOR
35 | Power Source Mitigation of UPLB (The project title is - "Electrical System Improvement") |  |  |  | 72000000 | [8 empty] | 0 |  |  | Ongoing upgrading of UPLB overhead and underground cable distribution system and transformers Phase 1 (Installation of Shielded Cables in Forestry) is 100% done. Phases 2 and 3 (Installation of Shielded Cable at Lower Campus) are currently in design phase. Phase 4 (LED streetlights) is currently in PR/information dissemination stage. PR materials being finalized - Status updated as of 19 May 2015
36 | Construction of Additional Two Storey Building for UP RURAL Highschool |  |  |  | 24000000 |  | UPLB RF | [6 empty] | 0 |  |  | preparation of TOR is ongoing
37 | Water System Improvement Phase 1) |  |  |  | 40000000 | [8 empty] | 0 |  |  | preparation of PR for rehabilitation of Deepwell Num 8 is ongoing
38 | UPLB Gender Center | [12 empty] | 0 |  |  | Pre-procurement meeting already held
39 | UPLB Veterinary Teaching Hospital (VTH) |  |  |  | 300000000 | [8 empty] | 0 |  |  | TOR is completed
40 | Extension of the Agronomy-Soil Science-Horticulture (ASH) Building, Crop Protection Center | [12 empty] | 0 |  |  | preparation of TOR is ongoing
41 | Central Experiment Station Building, College of Agriculture |  |  |  | 7000000 |  | UPLB RF | [6 empty] | 0 |  |  | preparation of TOR is ongoing
42 | Renovation of Dairy Technology Development Building and Dairy Administration Building (DTRI), College of Agriculture |  |  |  | 81000000 |  | UPLB RF | [6 empty] | 0 |  |  | preparation of TOR is ongoing
43 | Central Food Processing Research and Development Center, College of Agriculture |  |  |  | 60000000 | [8 empty] | 0 |  |  | preparation of TOR is ongoing
44 | Construction of National Plant Genetics Resources laboratory Building |  |  |  | 60000000 |  | UPLB RF | [6 empty] | 0 |  |  | preparation of TOR is ongoing
45 | Four-Storey Nanotechnology Center Building, Institute of Chemistry, CAS |  |  |  | 22000000 |  | TFI | [6 empty] | 0 |  |  | TOR is completed Status updated as of 19 May 2015
46 | Electrical Engineering Building, Phase 2, CEAT |  |  |  | 87000000 |  | TFI 2014 | [6 empty] | 0 |  |  | preparation of TOR is ongoing
47 | Condotel Staff housing |  |  |  | 100000000 |  | Endowment fund 2014 | [6 empty] | 0 |  |  | Preparation of TOR is ongoing Status updated as of 19 May 2015
48 | Construction of new building for ICS and INSTAT |  |  |  | 80000000 |  | TFI 2014 | [6 empty] | 0 |  |  | preparation of TOR is ongoing
49 | Establishment of Academic Multi Purpose Hall |  |  |  | 75000000 |  | TFI 2014 | [6 empty] | 0 |  |  | preparation of TOR is ongoing
50 | SESAM Annex Building to house the Interdisciplinary Studies Center |  |  |  | 42000000 |  | UPLB RF | [6 empty] | 0 |  |  | For preparation of TOR
51 | Community Media Center and DEVCOM Museum |  |  |  | 40000000 |  | TFI 2013 | [6 empty] | 0 |  |  | For preparation of TOR
52 | Renovation of Dormitories |  |  |  | 40000000 |  | TFI 2014 | [6 empty] | 0 |  |  | For preparation of TOR
53 | Renovation of SU building |  |  |  | 27500000 |  | UPLB RF | [6 empty] | 0 |  |  | Suggested for Job Contract
54 | Establishment of State of the Art Forestry Nursery |  |  |  | 25000000 |  | TFI 2014 | [6 empty] | 0 |  |  | For preparation of TOR
55 | Renovation of Obdulia Sison Hall (CEC) |  |  |  | 24500000 |  | Endowment fund 2014 | [6 empty] | 0 |  |  | Suggested for Job Contract
56 | Renovation of IHNF-CHE building |  |  |  | 17500000 |  | TFI 2014 | [6 empty] | 0 |  |  | Suggested for Job Contract
57 | Renovation of Old DAERS Building |  |  |  | 10000000 |  | UPLB RF | [6 empty] | 0 |  |  | Architectural plan completed Engineering Design ongoing - Status updated as of 19 May 2015
58 | Repair and Rehabilitation of Veterinary teaching Hospital at los Banos |  |  |  | 9000000 |  | TFI 2014 | [6 empty] | 0 |  |  | In-house design is ongoing
59 | Renovation of IPB laboratories and offices |  |  |  | 8000000 |  | UPLB RF | [6 empty] | 0 |  |  | For in-house design - Status updated as of 19 May 2015
60 | Renovation of International House |  |  |  | 7000000 |  | Endowment fund 2014 | [6 empty] | 0 |  |  | Renovation is ongoing
61 | Rehabilitation and Upgrading of the Wastewater Treatment Facility of BIOTEC Pilot Plant |  |  |  | 7000000 |  | UPLB RF | [6 empty] | 0 |  |  | For assessment with help from CEAT - Status updated as of 19 May 2015
62 | Construction of CINTERLABS on the 4th floor of IMSP Building |  |  |  | 7000000 |  | TFI 2014 | [6 empty] | 0 |  |  | In-house design is ongoing
63 | Replacement of CDC and Samonte Hall Roofing |  |  |  | 6000000 |  | UPLB RF | [6 empty] | 0 |  |  | For CDC Roofing: Architectural design completed Electrical design ongoing Architectural assessment ongoing For Samonte Hall: For preparation of architectural plans - Status updated as of 19 May 2015
64 | Completion of REDREC Building |  |  |  | 6000000 |  | UPLB RF | [6 empty] | 0 |  |  | scope of work for the 6M available money is being identified
65 | Completion of REDREC Building Phase 2 |  |  |  | 6000000 |  | UPLB RF | [6 empty] | 0 |  |  | scope of work for the 6M available money is being identified
64 | Completion of REDREC Building Phase 3 |  |  |  | 6000000 |  | PDAF (Zubiri) | [6 empty] | 0 |  |  | scope of work for the 6M available money is being identified
64 | Completion of REDREC Building Phase 4 |  |  |  | 3751000 |  | UPLB FI | [6 empty] | 0 |  |  | scope of work for the 6M available money is being identified (simultaneous with Phases 2 and 3)
66 | Completion of CEM plaza |  |  |  | 2500000 |  | UPLB RF | [6 empty] | 0 |  |  | Architectural plans completed PR already prepared by end-user - Status updated as of 19 May 2015
67 | Renovation of operations room (AG Samonte Hall) |  |  |  | 2000000 |  | UPLB RF | [6 empty] | 0 |  |  | for in-house design
68 | Reroofing of Copeland Gym |  |  |  | 4000000 |  | UPLB RF |  | 2 |  |  |  |  | 0 |  |  | Two failed biddings
69 | Supply, Delivery, Installation, and Commissioning of Electromagnetic Flowmeter Air Release Valve including appurtenant Works at Various Locations in UPLB |  |  |  | 3530000 |  | UPLB RF |  | 1 |  |  |  |  | 0 |  |  | Bidded out on 07 May 2015 For TWG's evaluation - Status updated as of 19 May 2015
70 | Profiling of Economically Important Disease of Swine and Cattle in the Philippines for Enhanced Disease Management Surveillance and Control (PL480) |  |  |  | 24000000 |  | Foreign assisted | [6 empty] | 0 |  |  | TOR for A&E are being finalized
71 | Conversion of classroom into Computer Laboratory, 4th Floor, Room 410, CAS Annex 1 |  |  |  | 992685.82 |  | UPLB RF | [6 empty] | 0 |  |  | Bidded out on 30 Apr 2015 For TWG's evaluation - Status updated as of 19 May 2015
72 | Construction of Faculty Room Extension, Dept of IE, CEAT | [5 empty] | UPLB RF | [6 empty] | 0 |  |  | For Bidding
73 | Repainting of Exterior Walls Including Roofing Sheets and Waterproofing of Roof Slab and Parapet Wall, Bldg A, CEAT |  |  |  | 929533.37 |  | UPLB RF | [6 empty] | 0 |  |  | For Bidding
74 | Supply, Delivery, Installation, and Commissioning of KWHR meters including Appurtenant works |  |  |  | 4007981.59 |  | UPLB RF | [6 empty] | 0 |  |  | For Bidding
75 | [13 empty] | 0
76 | [13 empty] | 0