## UP MANILA
OFFICE OF THE VICE PRESIDENT FOR DEVELOPMENT
INFRASTRUCTURE PROJECTS
OCTOBER 2014
UP MANILA
100
| PROJECT | PROJECT DESCRIPTION | DESIRED PROJECT OUTCOME | BUDGET (PhP) | CONTRACT PRICE (PhP) | ACTUAL COST (PhP) | SOURCE OF FUNDS | Contractor/Vendor | No. of Biddings | Date of Notice of Award | Date of Notice to Proceed | TARGET START DATE | ACTUAL START DATE | % ACCOMPLISHMENT | TARGET COMPLETION DATE | ACTUAL COMPLETION DATE | REMARKS (Problems/Issues Encountered and Other Pertinent Information Regarding the Project) | PROGRESS BILLING 1 | PROGRESS BILLING 2 | PROGRESS BILLING 3 | PROGRESS BILLING 4 | PROGRESS BILLING 5 | PROGRESS BILLING 6 | PROGRESS BILLING 7 | PROGRESS BILLING 8 | PROGRESS BILLING 9 | PROGRESS BILLING 10
1 | Renovation and Upgrading of the Pharmacology and Toxicology Lab (College of Medicine) | Renovation of the Pharmacology and Toxicology laboratory, installation of laboratory furniture, purchase of ultra high performance liquid chromatography UV-VIS and drug monitoring machine | Enhanced learning/research environment and increased research productivity |  |  |  | 2012 CHED Funding | [6 empty] | 0
2 | Modernization of Information Technology Center (Transfer to the Old CD Postgraduate Building) | Upgrading/modernization of the IT Center to include physical renovation works and acquisition/ installation of of office furniture | Enhanced learning/research environment and increased research productivity |  |  |  | 2012 CHED Funding | [6 empty] | 0 |  | 2014-09-18 | Inaugurated on 18 Sep 2014
3 | Laboratories for the National Institutes of Health | Upgrading/modernization and physical renovation of the Central Laboratory, including acquisition and installation of lab equipment and office furniture | Enhanced learning/research environment and increased research productivity |  |  |  | 2012 CHED Funding | [6 empty] | 0
4 | National Institutes of Health Building Project | Design and construction of the new National Institutes of Health (NIH) building | Enhanced learning/research environment and increased research productivity | 1000000000 |  |  | 2013 CO Budget | [6 empty] | 0 |  |  | To be bid via DBM Procurement Service Status updated as of 11 May 2015
5 | Conversion of Existing CAS Little Theater into the UP Manila Theater | Conversion of the College of Arts & Sciences (CAS) Theater into the UP Manila Theater | Improved access to academic support facilities and services for UP students, faculty & staff | 20000000 |  |  | 2014 CO Budget (CIDP) |  |  | 2013-11-20 |  |  |  | 100 |  | 2014-05-28 | Completed as of 28 May 2014
6 | Repair and Rehabillitation of Academic Buildings, including Purchase of Equipment (SHS-Tacloban) | Repair and rehabilitation of the academic buildings of the School of Health Science-Palo (currently located in the UPV-Tacaloban campus), and acquisition of equipment | Enhanced learning/research environment and increased research productivity | 26627000 |  |  | 2014 CO Budget | [6 empty] | 0 |  |  | For finalization of plans; for public bidding
7 | Modernization of Lab, Research and Teaching Equipment | Modernization of Laboratory, Research and Teaching Equipment | Enhanced learning/research environment and increased research productivity | 200000000 |  |  | 2015 CO Budget (NEP) | [6 empty] | 0 |  |  | For BAC review of SPPMP Has purchase request Status updated as of 11 May 2015
8 | Sports and Wellness Center (Central Administration and College of Medicine) |  |  | 30000000 |  |  | TFI | [6 empty] | 0 |  |  | For rebidding
9 | Sports and Wellness Center (Phase 2) |  |  | 60000000 | [9 empty] | 0 |  |  | Included in the budget proposal for buildings and structures for 2015; architectural plan completed
10 | Renovation of UP Manila Student Center and Joaquin Gonzales Hall (Central Administration) | Renovation and rehabilitation of the UP Manila Student Center and the Joaquin Gonzales Hall (Central Administration building) | Enhanced learning/research environment and increased research productivity | 2590000 |  |  | TFI | [6 empty] | 0 |  |  | Ongoing public bidding
11 | Construction of Student Lounge, Expansion of Library, Alumni and Graduate Program Office (College of Allied Medical Professions) |  |  | 111000 |  |  | TFI | [6 empty] | 0 |  |  | Preparation of detailed design and scope of works
12 | DPSM Computer Labs and Rooms (CAS) |  |  | 3000000 |  |  | TFI | [6 empty] | 0 |  |  | Revision of cost estimates
13 | Construction of Additional Classrooms and Labs at Gusaling Andres Bonifacio (CAS) |  |  | 1695000 |  |  | TFI | [6 empty] | 0 |  |  | Detailed plans, scope of works and cost estimates for end-user approval
14 | Renovation of Speech lab (CAS) |  |  | 1160000 |  |  | TFI | [6 empty] | 0 |  |  | Detailed plans, scope of works and cost estimates for end-user approval
15 | Extension and Modernization of Prosthodontics Lab (College of Dentistry) | [5 empty] | TFI | [6 empty] | 0 |  |  | Preparation of detailed design, scope of works and cost estimates
16 | Various Renovation Works at Paz Mendoza and Calderon Hall (College of Medicine) | Renovation of the Pharmacology and Toxicology laboratory, installation of laboratory furniture, purchase of ultra high performance liquid chromatography UV-VIS and drug monitoring machine | Enhanced learning/research environment and increased research productivity | 340000 |  |  | TFI | [6 empty] | 0 |  |  | For discussion between CPDMO and end-users for the scope of works
17 | Various Renovation Works at Sotejo Hall-Phases 1 and 2 (College of Nursing) |  |  | 1720000 | [9 empty] | 0 |  |  | For revision of cost estimates as suggested by technical consultant
18 | Repair of Roof Leaks due to Typhoon Glenda (College of Pharmacy) | [12 empty] | 0 |  |  | For revision of cost estimates as suggested by technical consultant
19 | Various Renovation Works at Valenzuela Hall, Upgrading of Dean's Complex, including De-clogging of Sewer Lines (College of Pharmacy) |  |  | 1806500 |  |  | TFI | [6 empty] | 0 |  |  | Preparation of detailed plans and other technical documents
20 | UP Manila Student Dormitory | Construction of a new dormitory for UP Manila students | Improved access to on-campus accommodation for UP students | 35000000 |  |  | TFI | [6 empty] | 0 |  |  | Phi Foundation will donate the design of the Phi House dormitory
21 | Supply and Installation of Passenger Elevator including Design and Construction of Elevator Shaft (CAMP) |  |  | 4500000 |  |  | TFI | [6 empty] | 0 |  |  | TOR and other bidding documents approved
22 | Construction of Computer Lab; Provision of 3rd Floor at the College of Public Health Annex Building | Construction of Computer Lab; Provision of 3rd Floor at the College of Public Health Annex Building | Enhanced learning/research environment and increased research productivity | 6619000 |  |  | UP System RF | [6 empty] | 0 |  |  | Bid documents submitted to BAC2
23 | Construction of SHS-Baler, Aurora Campus Phase 2: (1) Academic Building 2, Administrative Building and Birthing Center and (2) Power House and Entrance Cable | Construction of the School of Health Sciences (SHS) building (Phase 2) in the UP Manila Baler, Aurora campus | Enhanced learning/research environment and increased research productivity | 30000000 |  |  | UP System RF | [6 empty] | 0 |  |  | Draft TOR presented to the SBAC; technical specs being reviewed by the TWG; concern: trees will be affected
24 | Supply and Installation of Transformers | Supply & Installation of Transformers | Improved working environment for UP administrators, faculty, students & staff | 875000 |  |  | UP System RF | [6 empty] | 0 |  |  | Work suspended awaiting construction of power house and entrance cable
25 | Dismantling and Disposal of Asbestos-Containing Materials (SHS-Palo) |  |  | 747000 | [9 empty] | 0 |  |  | Contract signed by the Chancellor
26 | Additional Works for the Completion of the 4th Floor (College of Dentistry) |  |  | 810000 |  |  | TFI | [6 empty] | 0 |  |  | Ongoing
27 | Structural Integrity Testing (CAMP) |  |  | 300000 |  |  | TFI | [6 empty] | 0 |  |  | Ongoing
28 | Structural Integrity Testing (College of Nursing) |  |  | 300000 |  |  | TFI | [6 empty] | 0 |  |  | Ongoing
29 | Student Center (CAS) |  |  | 10000000 |  |  | TFI | [6 empty] | 0 |  |  | Awarded; awaiting building permit from City of Manila
30 | Reroofing and Waterproofing of UPCM Library |  |  | 996000 |  |  | TFI | [6 empty] | 0 |  |  | Ongoing
31 | College of Dentistry-Exterior Repainting of 4th Floor | [5 empty] | Construction of the 4th floor completed but exterior painting was not included in the scope of works | [6 empty] | 0
32 | College of Pharmacy-Repair of Sewer Lines |  |  | 1800000 |  |  | With preliminary technical documents | [6 empty] | 0
33 | NTTCHP-Learning Resource Unit |  |  | 5000000 |  |  | With floor plan and layout | [6 empty] | 0
34 | University Library-Upgrading of Discussion Room and Learning Commons |  |  | 2500000 |  |  | With preliminary technical documents | [6 empty] | 0
35 | SHS-Tacloban Rehabilitation |  |  | 565200000 |  |  | Included in the 2015 budget proposal for building and structures | [6 empty] | 0
36 | Torch 1 |  |  | 250000000 |  |  | Included in the 2015 budget proposal for buildings and structures; building perspectives completed | [6 empty] | 0
0
294 | Renovation of Lab |  |  | 9511759 | 8380645 |  |  | Ritvit Construction & Development Corporation | [5 empty] | 0 |  |  | NTP issued but not yet accepted; site not ready, pending reroofing of Salcedo Hall (not CHED-funded; for rebidding)
294 | Supply and Installation of Lab Furniture |  |  | 5414723 | 2660208 |  |  | Elite Scientific & Diagnostic Supplies Company |  |  | 2014-09-30 |  |  | 0 |  |  | For issuance of NTP as of 30 Sep 2014; work suspended, awaiting completion of renovation works
294 | Purchase of Ultra High Performance Liquid Chromatography UV-VIS |  |  | 5273320 | 4480000 |  |  | RainPhil Inc. | [5 empty] | 0 |  | 2014-05-09 | Delivered as of 09 May 2014
294 | Purchase of Drug Monitoring Machine (Architect C400 Analyzer) |  |  | 7500000 | 7500000 |  |  | Elite Scientific & Diagnostic Supplies Company | [5 empty] | 0 |  |  | Negotiated procurement; PO for signature of the Chancellor as of 25 Jun 2014
295 | Physical Renovation Works |  |  | 8911785 | 8908158 | 9793293.36 |  | ASM Francisco Construction & Development Corporation |  |  | 2013-09-02 |  |  | 0 |  | 2014-09-01 | Completed as of September 2014
295 | Supply and Installation of Office Furniture |  |  | 1409993 | 1049900 |  |  | Roseco Marketing Ventures |  | 2013-06-12 |  |  |  | 0 |  | 2014-09-01 | Completed as of September 2014
296 | Balancing of Existing Electrical Load |  |  | 490538 | 476250 |  |  | Power Compact Enterprises | [5 empty] | 100 |  | 2013-07-24 | Completed as of 24 Jul 2013
296 | Physical Renovation of the Central Lab |  |  | 7273705 | 5788243 |  |  | ASM Francisco Construction & Development Corporation |  | 2013-03-14 |  |  |  | 70 |  |  | work suspended 15 Jul-19 Aug 2013 due to transfer of lab equipment; work resumed on 20 Aug 2013; implemented in phases as a result; Phase 1 completed; Phase 2: 70% complete as of 02 Oct 2014; delay caused by Microarray lab relocation
296 | Consulting Services for the Development of Design Intent & Certification of a Modular Biosafety Level 3 Facility |  |  | 2300000 | 2100000 |  |  | Basler & Hoffman Singapore Pte. Ltd. |  | 2013-07-30 | 2014-01-06 |  |  | 0 |  |  | contract duration: 12 months; consultancy services ongoing
296 | Design and Build for BSL 3 |  |  | 32000000 | 30639383 |  |  | Tochigi-Ken Technologies International Inc. | [5 empty] | 0 |  |  | Contract being processed as of 02 Oct 2014; for approval by PAEP
296 | Supply and Installation of Lab Furniture at BSL Facilities |  |  | 2625325 | 1275420 |  |  | Elite Scientific & Diagnostic Supplies Company | [5 empty] | 0 |  |  | For issuance of NTP
296 | Supply and Installation of Lab Furniture at BSL 2 and the Central Lab |  |  | 3441567 | 2491873 |  |  | Elite Scientific & Diagnostic Supplies Company |  |  | 2013-07-01 |  |  | 60 |  |  | with various suspension orders; delivery made in phases depending on the progress of renovation works; 60% complete as of 31 Oct 2014
296 | Renovation of BSL Facility |  |  | 4035660 | 3918117 |  |  | Tochigi-Ken Technologies International Inc. |  | 2013-05-24 | 2013-08-22 |  |  | 89 |  |  | with various suspension orders due to difficulty in transferring lab equipment; suspended since 18 Feb 2014