## UP MINDANAO
OFFICE OF THE VICE PRESIDENT FOR DEVELOPMENT
INFRASTRUCTURE PROJECTS
OCTOBER 2014
UP MINDANAO
100
| PROJECT | PROJECT DESCRIPTION | DESIRED PROJECT OUTCOME | BUDGET (PhP) | CONTRACT PRICE (PhP) | ACTUAL COST (PhP) | SOURCE OF FUNDS | Contractor/Vendor | No. of Biddings | Date of Notice of Award | Date of Notice to Proceed | TARGET START DATE | ACTUAL START DATE | % ACCOMPLISHMENT | TARGET COMPLETION DATE | ACTUAL COMPLETION DATE | REMARKS (Problems/Issues Encountered and Other Pertinent Information Regarding the Project) | PROGRESS BILLING 1 | PROGRESS BILLING 2 | PROGRESS BILLING 3 | PROGRESS BILLING 4 | PROGRESS BILLING 5 | PROGRESS BILLING 6 | PROGRESS BILLING 7 | PROGRESS BILLING 8 | PROGRESS BILLING 9 | PROGRESS BILLING 10
1 | Construction of Two-Storey Library | Construction of Phase 1 of UP Mindanao's two-storey library, with the following features: gallery, records rooms, AVR, reading areas, Internet & multi-media rooms, business areas for bookstore & coffee shop | Enhanced learning/research environment and increased research productivity | 28436011 |  |  | 2012 CHED Funding |  |  | 2012-11-14 | 2013-01-11 |  | 2013-10-17 | 100 |  | 2014-08-03 | Total floor area: 1,000.35 sqm. Completed as of Aug 2014 Soft opening on 06 May 2015
2 | Renovation of CSM Building and Rehabilitation of Basketball Court | Renovation of the College of Science & Mathematics building, and the rehabilitation of the campus covered basketball court | Improved access to academic support facilities and services for UP faculty, students & staff |  | 1057000 |  |  | P-Square Associates Co. | Completed as of Jul2014 |  |  |  |  | 0
3 | Completion of Dormitory Building |  |  | 140000000 |  |  | 2014 CO Budget |  | 1 |  |  |  |  | 0 |  | 2014-09-01 | Completed as of September 2014; waiting for occupancy permit and final turnover
4 | CHHS Cultural Complex Building | Construction of the College of Humanities and Social Sciences Cultural Complex building, a venue for the arts, anthropology and architectural heritage of Mindanao in the University | Improved access to academic support facilities and services for UP students, faculty & staff | 31400000 |  |  | 2015 CO Budget (NEP) | A.C. Ong | 1 | 2015-01-28 |  |  |  | 3 |  |  | A.C. Ong Consulting representative Arch. Arnel de Guia met with UPMin representatives (Campus Planning & Development Team, CHHS Project Team, and Physical Plant Office) to discuss architectural revisions. - Architectural revisions will be submitted by contractor during the last week of May 2015 - Status updated as of 11 May 2015
5 | Rehabilitation of SOM & HKC Road | Rehabilitation/concreting of roads and repair of drainage canals in affected areas of the UP Mindanao campus | Improved working environment for UP administrators, faculty, students & staff | 4000000 | 4830992.51 |  | UP Mindanao GF | Algon Engineering Construction Corporation | 2 |  |  |  |  | 40 | 2015-06-11 |  | Two failed biddings The SOM & HKC Road leads to the proposed site of the College of Humanities & Social Sciences (CHSS) Cultural Complex. Status Updated as of 11 May 2015
6 | Repair of Drainage Canal along Bagobo Road near University Infirmary |  |  | 1000000 | 959755.36 |  | UP Mindanao GF | Algon Engineering Construction Corporation | 2 | 2015-02-27 | 2015-03-17 |  |  | 0 |  |  | Contract is expected to be signed anytime in May 2015 - Status updated as of 11 May 2015
7 | Establishment of Center for Advancement of Research in Mindanao (CARIM-UP Mindanao) | Construction of the Center for Advancement of Research in Mindanao (CARIM) building (Phase 1) | Enhanced learning/research environment and increased research productivity | 15000000 |  |  | UP Mindanao GF UPOU Endowment Fund | [6 empty] | 0 |  |  | PhP 10M of the budget comes from the 2014 GAA. After four design revisions, the final design was submitted to ODPI on 25 Mar 2015. - ODPI's recommendations to improve the schematic/floor plans sent to UPMin on 30 Mar 2015. - Final working drawings currently being prepared for submission to the University - Status updated as of 11 May 2015
8 | Construction of CARIM Phase 2 |  |  | 1000000 |  |  | UPOU RF | [6 empty] | 0 |  |  | Bidding conducted on 20 Apr 2015 - TWG still evaluating bidders - Status updated as of 11 May 2015
9 | Acquisition of Various Lab, Research and Teaching Equipment | Acquisition of Various Lab, Research and Teaching Equipment | Enhanced learning/research environment and increased research productivity | 2400000 | [9 empty] | 0
10 | Improvement and Repair of Labs, Purchase and Upgrading of Equipment (CS and Math Buildings) | Renovation, improvement and rehabilitation of the College of Science & Mathematics (CSM), to include painting of the building façade, replacement of damaged doors, ceilings, walls and partitions, electrical wires and fixtures, as well as installation of floor tiles; also included the setting up of the decontaminating and washing area, and laboratory waste holding room | Enhanced learning/research environment and increased research productivity | 800000 |  |  |  |  | 1 |  |  | 2015-10-01 |  | 3 |  |  | Bidding conducted on 20 Apr 2015 Evaluation of bidders ongoing Status updated as of 11 May 2015
11 | Construction of Coconut Tissue Culture Lab Building | Construction of the Coconut Tissue Culture Laboratory at the Kalimudan Student Center, to include an office, a preparation room, a hot room, staff area, transfer room, and culture growth room | Enhanced learning/research environment and increased research productivity; improved access to academic support facilities | 1000000 |  |  | Philippine Council for Agriculture, Aquatic, and Natural Resources Research and Development (PCAARRD) | [6 empty] | 0 |  | 2014-09-01 | Completed as of September 2014 Inaugurated on 19 Mar 2015 Permanent power connected as of 16 May 2015
12 | Completion of School of Management Building |  |  | 10000 |  |  | UPOU RF | [6 empty] | 0 |  |  | Proposal submitted to UP System
13 | Repair of SOM Roofing |  |  | 80000 |  |  | UPOU RF | [6 empty] | 100 |  |  | Completed as of August 2014
14 | Repair of CHHS Building-Teaching Facilities |  |  | 350000 |  |  | UPOU RF | [6 empty] | 100 |  |  | Completed as of September 2014
15 | Rehabilitation of Comfort Rooms |  |  | 225000 |  |  | UPOU RF | [6 empty] | 0 |  |  | Proposal stage
16 | LED Lights Conversion |  |  | 1600000 | [9 empty] | 0 |  |  | For implementation 2014-2016
17 | Completion of Kalimudan Covered Court |  |  | 1500000 |  |  | API |  | 2 |  |  |  |  | 0 |  |  | Project aims to complete the 2/3 uncovered area of the Kalimudan Student Center court - Due to 2 failed biddings, UPMin has scheduled the submission of proposals from bidders who are interested to go into negotiations on 20 May 2015 - Status updated as of 11 May 2015
18 | Rehabilitation of Lawn, Tennis Court |  |  | 1000000 | [9 empty] | 0
19 | Completion of the SOM Building Phase 2 |  |  | 10000000 |  |  | TFI |  | 1 |  |  |  |  | 0 | 2015-09-01 |  | Architectural design awarded to Arch. Daniel Briones on 23 Jan 2015 Consultations with end-users ongoing Status updated as of 11 May 2015
20 | Davao City - University of the Philippines (DC-UP) Sports Complex | [12 empty] | 0 |  |  | UPMin, in partnership with the Davao City government, will construct a sports complex in a 20 hectare site inside UPMin. - MOU between two parties was approved by the Sangguniang Panglungsod on 28 April 2015. - Mayor Duterte is expected to sign the resolution ordinance anytime in May 2015. - MOU signing between Mayor Duterte and PAEP will be arranged as well. - Status updated as of 11 May 2015
21 | Concreting/Improvement of UP Mindanao |  |  | 50000000 |  |  | DPWH | [6 empty] | 0 |  |  | Aims to jumpstart the establishment of the DC-UP Sports Complex - PhP 50M earmarked by DPWH Region XI 2nd District Engineering Office (2DEO) via 2015 GAA. - Project bid out by DPWH DEO on 25 Jan 2015 - Survey team has yet been able to mark the road due to the presence of informal settlers - Status updated as of 11 May 2015
22 | Construction of Multi-Purpose Building |  |  | 100000000 | [9 empty] | 0 |  |  | DPWH Region XI's technical team is currently finalizing the detailed architectural plans of the structure. - Plans will be submitted to ODPI and OVPD for assessment upon their completion - Status updated as of 11 May 2015
23 | Construction of HKC Multi-purpose Building |  |  | 50000000 | [9 empty] | 0 |  |  | Structure is currently referred to as "Football Stadium" - Planned seating capacity is between 30,000 and 36,000 - Preliminary architectural designs have been submitted to 2DEO - Status updated as of 11 May 2015
24 | Construction of Football Field and Track Oval |  |  | 50000000 | [9 empty] | 0 |  |  | UPMin's Campus Planning and Development Team is closely working with OVPD-ODPI regarding the architectural plans for the track oval and football field. - Status updated as of 11 May 2015
25 | Construction/Improvement of the Oblation Plaza | [5 empty] | UPAA Davao Chapter | [5 empty] | 2015-02-28 | 0 |  |  | On 28 Feb 2015, roughly 500 people came to contribute their sweat equity for the construction/improvement of the Oblation Plaza. - Detailed plans of the Oblation Plaza included the installation of paver blocks for the Inner Circle, the installation of Legacy Tiles, and the construction of gabion blocks around the Oblation. - Status updated as of 11 May 2015
0
331 | - Renovation of CSM Building: Design |  |  |  | 27379011 |  |  | Ammarsons Construction & Services Corporation | Ongoing; 45% complete as of 30 Sep 2014 | 2012-10-12 | 2012-10-16 |  |  | 0 |  | 2013-12-05 | Completed as of 05 Dec 2013
331 | - Renovation of CSM Building: Construction |  |  | 1263989 | 1263989 |  | 2012 CHED Funding | Early Riser Construction | Completed as of 30 Apr 2014 | 2012-12-21 | 2013-01-11 |  |  | 0 |  | 2013-07-27 | Completed as of 27 Jul 2013
331 | - Rehabilitation of Basketball Court: Design | [8 empty] | 2012-10-12 | 2012-10-16 |  |  | 0 |  | 2013-12-05 | Completed as of 05 Dec 2013
331 | - Rehabilitation of Basketball Court: Construction | [8 empty] | 2012-12-21 | 2013-01-11 |  |  | 0 |  | 2013-03-14 | Completed as of 14 Mar 2013