## UPOU
OFFICE OF THE VICE PRESIDENT FOR DEVELOPMENT
INFRASTRUCTURE PROJECTS
OCTOBER 2014
UP OPEN UNIVERSITY
100
| PROJECT | PROJECT DESCRIPTION | DESIRED PROJECT OUTCOME | BUDGET (PhP) | CONTRACT PRICE (PhP) | ACTUAL COST (PhP) | SOURCE OF FUNDS | Contractor/Vendor | No. of Biddings | Date of Notice of Award | Date of Notice to Proceed | TARGET START DATE | ACTUAL START DATE | % ACCOMPLISHMENT | TARGET COMPLETION DATE | ACTUAL COMPLETION DATE | STATUS | PROGRESS BILLING 1 | PROGRESS BILLING 2 | PROGRESS BILLING 3 | PROGRESS BILLING 4 | PROGRESS BILLING 5 | PROGRESS BILLING 6 | PROGRESS BILLING 7 | PROGRESS BILLING 8 | PROGRESS BILLING 9 | PROGRESS BILLING 10
1 | Construction of UPOU Community Hub Building | The UPOU Community Hub will be constructed for the purpose of bringing UPOU closer to the general public which will house the museum, library and the information office | Improved access to academic support facilities and services for UP students, faculty & staff | 28436011 |  |  | 2012 CHED Funding | [6 empty] | 0
2 | Refurbishing of UPOU Learning Centers (Renovation of UPOU Learning Center in Iloilo | Refurbishing of UPOU learning centers (renovation of UPOU learning center in Iloilo) | Enhanced learning environment | 1263989 | 1263989 |  | 2012 CHED Funding | Early Riser Construction | 1 | 2013-06-25 | 2013-07-25 |  |  | 100 |  | 2014-04-30 | Completed as of 30 Apr 2014
3 | UPOU International Convention Center | The UPOU International Convention Center is envisioned to serve as the primary venue for international and national conferences for open and distance e-learning using state of the art telecommunications and multi-media facilities. | Improved access to academic support facilities and services for UP students, faculty & staff | 140000000 | 140,000,000+30,000,000 = 170,000,000 |  | 2014 GAA + UPOU Endowment Fund |  | 2 |  |  |  |  | 0 |  |  | Ongoing public bidding
4 | Provision of Green and Safe Environment Devices | Acquisition and installation of green and safe environment devices | Safer and eco-friendly working environment for UP administrators and stakeholders | 31400000 |  |  | 2015 GAA | [6 empty] | 0
5 | Installation of First Private Pole and Electrical Facilities | Installation of First Private Pole and Electrical Facilities | Improved working environment for UP administrators, faculty, students & staff | 5000000 | 4462272 | 4462272+445404.55 = 4907676.55 | UP System RF |  | 1 | 2014-03-04 | 2014-03-31 |  |  | 0 |  | 2014-11-15 | Completed as of 15 November 2014
6 | Construction of UPOU Teaching and Learning Hub | The proposed Teaching and Learning Hub will house the faculty and staff of the three (3) faculties of UPOU. |  | 15000000 | 1050000 |  | UPOU RF | [6 empty] | 0 |  |  | A and E ongoing
7 | Construction of Elevator Shaft |  |  | 480000 |  |  | UPOU RF | [6 empty] | 0
8 | Installation of Solar Panels at the UPOU Community Hub |  |  | 2400000 |  |  | 2012 CHED Funding | [6 empty] | 0 |  |  | Not bid
9 | Installation of Solar-Powered Streetlights | Installation of new and eco-friendly lights along the campus streets/walkways | Safer and eco-friendly working environment for UP administrators and stakeholders | 821351.443 |  |  | 2012 CHED Funding | [6 empty] | 0 |  |  | Not bid | documents with COA already | documents with COA already | documents with COA already | documents with COA already | 4137457.26
10 | Provision of Rainwater Collector Pond |  |  | 1000000 |  |  | 2012 CHED Funding | [6 empty] | 0 |  |  | Not bid
11 | Demolition of Parapet Wall |  |  | 9653.84 | 8000 | 8000 | UPOU RF | RQ Torres Construction | 1 |  |  |  |  | 0 |  |  | Completed
12 | Repair of Ceiling Eaves and Replacement of Polycarbonate Roofing Sheets at IMDPO and Learners Hall |  |  | 86693.5 | 86693..44 | 86693.44 | UPOU RF | RC De Villa Construction | 1 | 2015-02-16 |  |  |  | 0 |  |  | Contract in process
13 | Installation of Glass Panel Wall and Doors at the Admin Building |  |  | 312194 | 312194 | 312194 | UPOU RF | SMJ Glass, Aluminum and Metal Works | 1 | 2015-02-16 |  |  |  | 0 |  |  | Proposal stage
14 | Application of Asphalt Overlay |  |  | 350901.6 | 350901.6 | 350901.6 | UPOU RF | Silver Grey Enterprises | 1 | 2015-02-16 |  |  |  | 0 |  |  | Proposal stage
15 | Provision of Covered Parking and Construction of Storage Room | [12 empty] | 0 |  |  | Proposal stage
0
355 | Design Preparation Phase: A&E Design Services |  |  | 1057000 | 1057000 | 1057000 | 2012 CHED Funding | P-Square Associates Co. | 1 | 2012-07-25 | 2012-07-27 |  |  | 100 |  | 2013-07-01 | Completed as of Jul2013
355 | Building Construction Phase |  |  | 27379011 | 27379011 | 21787389.85 | 2012 CHED Funding | Ammarsons Construction & Services Corporation | 1 | 2013-06-25 | 23 Sept 2013 | 2013-10-01 | 2013-10-18 | 95.11 | 2015-03-20 |  | 95.11% complete as of Mar. 30, 2015. The contractor is charged for Liquidated Damages. Target date for completion of remaining works is May 30, 2015.