## UP PGH
OFFICE OF THE VICE PRESIDENT FOR DEVELOPMENT
INFRASTRUCTURE PROJECTS
OCTOBER 2014
UP PGH
| PROJECT | PROJECT DESCRIPTION | DESIRED PROJECT OUTCOME | BUDGET (PhP) | CONTRACT PRICE (PhP) | ACTUAL COST (PhP) | SOURCE OF FUNDS | Contractor/Vendor | No. of Biddings | Date of Notice of Award | Date of Notice to Proceed | TARGET START DATE | ACTUAL START DATE | % ACCOMPLISHMENT | TARGET COMPLETION DATE | ACTUAL COMPLETION DATE | REMARKS (Problems/Issues Encountered and Other Pertinent Information Regarding the Project) | PROGRESS BILLING 1 | PROGRESS BILLING 2 | PROGRESS BILLING 3 | PROGRESS BILLING 4 | PROGRESS BILLING 5 | PROGRESS BILLING 6 | PROGRESS BILLING 7 | PROGRESS BILLING 8 | PROGRESS BILLING 9 | PROGRESS BILLING 10
1 | Purchase of MRI, CT Scan and Other Urgently Needed Equipment | Purchase of MRI, CT Scan and Other Urgently Needed Equipment to better serve the Hospital's stakeholders | Improved public/community service | 140580000 |  |  | 2012 CHED Funding
2 | Acquisition of Medical Equipment for Expansion/ Development/Upgrading of Services | Acquisition of Medical Equipment for Expansion, Development and Upgrading of Services | Improved public/community service | 190000000 |  |  | 2012 CO Budget
3 | Acquisition of Medical Equipment for Expansion/ Development/Upgrading of Services | Acquisition of Medical Equipment for Expansion, Development and Upgrading of Services | Improved public/community service | 200000000 |  |  | 2014 CO Budget | [9 empty] | For public bidding
4 | Health Facilities Enhancement | Enhancement of health facilities to better serve the Hospital's stakeholders | Improved public/community service | 35000000 |  |  | 2014 CO Budget | [9 empty] | For public bidding
5 | Acquisition and Upgrading of Various Hospital Equipment | Acquisition and Upgrading of Various Hospital Equipment to better serve the stakeholders of PGH | Improved public/community service | 3150000000 |  |  | 2015 CO Budget (NEP) | [9 empty] | Bidding has started Status updated as of 13 May 2015
370 | Super Conductive MRI System |  |  |  | 72000000 |  |  | Marben Commercial | [8 empty] | Delivered as of 20 Feb 2014
370 | Various Medical Instruments |  |  |  | 2513297 |  |  | Respicare Enterprise | [8 empty] | Delivered as of 20 Feb 2014
370 | Low Temperature Sterilizer |  |  |  | 3188000 |  |  | Zuellig Pharma Corporation | [8 empty] | Delviered as of 20 Feb 2014
370 | Multi Detector Scan 64-series |  |  |  | 47820748 |  |  | Phillips Electronics | [8 empty] | Delivered as of 25 Jun 2014
370 | Anesthesia Machine/Patient Monitor |  |  |  | 5160000 |  |  | Technomed International | [8 empty] | Delivered as of 20 Feb 2014
370 | Optical Coherence Tomographer (OCT) |  |  |  | 9897955 |  |  | Microbiology Laboratory Inc. | [8 empty] | Delivered as of 25 Jun 2014
370 | Automatic Tissue Stainer |  |  |  | 1900000 |  |  | Guill-Bern Corporation | [8 empty] | Delivered as of 25 Jun 2014
370 | Computer System |  |  |  | 46900 |  |  | PCKlinik Inc. | [8 empty] | Delivered as of 25 Jun 2014
370 | Printer |  |  |  | 3450 |  |  | Accel Prime Technologies | [8 empty] | Delivered as of 25 Jun 2014
370 | Various Thoracic Instruments |  |  |  | 1009870 |  |  | Respicare Enterprises | [8 empty] | Delivered as of 25 Jun 2014
370 | Fiberoptic Bronchoscope |  |  |  | 1678000 |  |  | The Pharmedic Corporation | [8 empty] | Delivered as of 25 Jun 2014
370 | Bedside Multiparameter Cardiac Monitor |  |  |  | 112000 |  |  | Blue Sky | [8 empty] | Delivered as of 25 Jun 2014
370 | CPAP Machine |  |  |  | 21070 |  |  | Blue Sky | [8 empty] | Delivered as of 25 Jun 2014
370 | Blenders for Osterized Tube Feeding |  |  |  | 16620 |  |  | Lurebec Enterprises | [8 empty] | Delivered as of 25 Jun 2014
370 | H3+ Digital Holter Recorder Small and Lightweight, 1 ounce (24g) 3-channel recording |  |  |  | 100000 |  |  | MedEV Medical Devices Corporation | [8 empty] | Delivered as of 25 Jun 2014
370 | Water Boiler |  |  |  | 8990 |  |  | Lurebec Enterprises | [8 empty] | Delivered as of 25 Jun 2014