## UP VISAYAS
OFFICE OF THE VICE PRESIDENT FOR DEVELOPMENT
INFRASTRUCTURE PROJECTS
OCTOBER 2014
UP VISAYAS
100
| PROJECT | PROJECT DESCRIPTION | DESIRED PROJECT OUTCOME | BUDGET (PhP) | CONTRACT PRICE (PhP) | ACTUAL COST (PhP) | SOURCE OF FUNDS | Contractor/Vendor | No. of Biddings | Date of Notice of Award | Date of Notice to Proceed | TARGET START DATE | ACTUAL START DATE | % ACCOMPLISHMENT | TARGET COMPLETION DATE | ACTUAL COMPLETION DATE | REMARKS (Problems/Issues Encountered and Other Pertinent Information Regarding the Project) | PROGRESS BILLING 1 | PROGRESS BILLING 2 | PROGRESS BILLING 3 | PROGRESS BILLING 4 | PROGRESS BILLING 5 | PROGRESS BILLING 6 | PROGRESS BILLING 7 | PROGRESS BILLING 8 | PROGRESS BILLING 9 | PROGRESS BILLING 10
1 | Project A |  |  | 13860000 | 13723760 |  | 2012 CHED Funding | [6 empty] | 0
2 | Project B |  |  | 13860000 | 13723760 |  | 2012 CHED Funding | [6 empty] | 0
3 | Construction of Student Dormitory | Construction of Student Dormitory | Improved access to on-campus accommodation for UP students | 21500000 |  |  | 2013 CO Budget | [6 empty] | 61 |  |  | Expected date of completion was March 20, 2015. Pending request for extension for 45 days was endorsed for approval.
4 | Indigenous Center under the Center for West Visayan Study | Construction of the Indigenous Center under the Center for West Visayan Study | Enhanced learning/research environment and increased research productivity | 2000000 |  |  | 2014 CO Budget | [6 empty] | 0 |  |  | Ongoing Preparation of Plans and Program of Works Status updated as of 11 May 2015
5 | Renovation of College of Arts and Science Lab Rooms 1 and 2, Miag-ao | Renovation of College of Arts and Science Lab Rooms 1 and 2, Miag-ao | Enhanced learning/research environment and increased research productivity | 2000000 |  |  | 2014 CO Budget | [6 empty] | 0
6 | Renovation of the Psychology Lab, CAS | Renovation of the Psychology Lab, College of Arts and Sciences | Enhanced learning/research environment and increased research productivity | 1000000 |  |  | 2014 CO Budget | [6 empty] | 100 |  | 2014-01-24 | Completed as of 24 Jan 2014
7 | Rehabilitation of CAS Classrooms and Lab | Rehabilitation and renovation of classrooms and laboratory of the College of Arts & Sciences | Enhanced learning environment | 4400000 |  |  | 2014 CO Budget | [6 empty] | 0
8 | Construction of Research Center | Construction of the Research Center building | Enhanced learning/research environment and increased research productivity | 20000000 |  |  | 2015 CO Budget (NEP) | [6 empty] | 1 |  |  | Conduct of Soil Testing & Geodetic Survey on Project Site Status updated as of 11 May 2015
9 | Construction of School of Technology Building | Construction of School of Technology Building | Enhanced learning environment | 25000000 |  |  | 2015 CO Budget (NEP) | [6 empty] | 1 |  |  | Conduct of Soil Testing & Geodetic Survey on Project Site Status updated as of 11 May 2015
10 | Construction of Bamboo Village Phase 2 | Construction of Bamboo Village (faculty & staff housing) Phase 2 | Improved access to on-campus housing for UP faculty & staff; increased productivity | 10000000 |  |  | 2015 CO Budget (NEP) | [6 empty] | 1 |  |  | Ongoing Preparation of Plans and Program of Works Status updated as of 11 May 2015
11 | Construction of Taklong Island Marine Reserve Research Quarters |  |  | 4000000 |  |  | 2015 CO Budget (NEP) | [6 empty] | 100 |  | 2009-01-01 | Completed as of Jan 2009
12 | Renovation of Audio Room, UPV Auditorium, Iloilo City Campus |  |  | 50176 |  |  |  | In-house | [5 empty] | 0 |  |  | Materials are now with CDMO; canvass for supply of labor ongoing through SPSO
13 | Security Service and Fire Station-Procurement of Labor and Materials |  |  | 486310 | [9 empty] | 0 |  |  | Pre-bid conference conducted on 01 Sep 2014; awaiting delivery of materials by SPSO
14 | LBP ATM Booth, Iloilo City Campus |  |  | 25149 | [9 empty] | 0 |  |  | Bids are higher than the approved budget; CDMO recommended in-house implementation
15 | Two-Storey Student Dormitory, Miag-ao Campus |  |  | 21500000 | 18859307 |  |  | Legacy Construction | [5 empty] | 0 |  |  | Ongoing; 30.68% complete as of 30 Sep 2014; implementation ahead of schedule; target completion: 03 Feb 2015
16 | Renovation of Accounting Office, Miag-ao Campus |  |  | 657060 | 640672 | 640672 |  | Camcu Construction & Supply | [5 empty] | 100 |  |  | Completed as of 06 Jul 2014
17 | Stockroom Extension, UPV Library, Miag-ao Campus |  |  | 303334 | [9 empty] | 0 |  |  | Approval received on 07 May 2014; work started on 01 Oct 2014
18 | Two Units Single Bedroom House at Bambusa Village (Phase 1), Miag-ao Campus |  |  | 1000000 |  |  |  | In-house | [5 empty] | 0 |  |  | Pre-bid conducted on 01 Sep 2014; procurement by SPSO ongoing
19 | Construction of Multi-Purpose Building, Diwata Shore Project (Oceanarium) Phase 2; Completion of Aquaria and Related Works, Miag-ao Campus |  |  | 3358256 | 3257001 |  |  | FLT Enterprises | [5 empty] | 0 |  |  | NTP issued on 23 Feb 2014; 23 May 2014 time extension 1 (23 Jun 2014); time extension 2 (15 days): 08 Jul 2014; 98% complete as of 30 Sep 2014
20 | Replacement of Leaking Roof, UPV Diliman Guest House |  |  | 218546 | [9 empty] | 0 |  |  | Approved copy received by CDMO on 25 Feb 2014; for implementation by UPV Diliman Liaison Office
21 | Extension of Office of Student Affairs, Miag-ao Campus |  |  | 1587554 | [9 empty] | 0 |  |  | Revised plan of work for cost updating; for budget appropriation
22 | Repair of Cluster 2, Unit 4, UPV Staff Housing, Miag-ao Campus |  |  | 72513 |  |  |  | In-house | [5 empty] | 0 |  |  | Materials with SPSO
23 | Construction of Three Monopole Towers (Miag-ao, Iloilo City and Taklong, Gimaras) |  |  | 821280 | [9 empty] | 0 |  |  | Procurement ongoing: public bidding conducted on 01 Sep 2014, but failed
24 | Conversion of Bowling Alley into Lecture Rooms, Miag-ao Campus |  |  | 759579 |  |  |  | In-house | [5 empty] | 0 |  |  | 62% complete; awaiting delivery of materials
25 | Construction of Physical Education Dance Studio with Comfort Rooms at Covered Court |  |  | 1024456 | [9 empty] | 0 |  |  | For approval; endorsement forwarded on 13 Aug 2014
26 | Facilitation of Five Platforms for Benches, CAS, Miag-ao Campus |  |  | 22570 |  |  |  | In-house | [5 empty] | 0 |  |  | For implementation; CDMO to do overtime work
27 | Renovation of Psychology Laboratory, CAS, Miag-ao |  |  | 493002 | [9 empty] | 0 |  |  | For procurement; approval received on 24 Feb 2014; pre-bid conference conducted on 01 Sep 2014
28 | Fabrication of Service Counter in TLRC, Miag-ao Campus |  |  | 32837 | [9 empty] | 0 |  |  | TLRC to outsource the job
29 | Renovation of Computer Science Lab Rooms 1&2 and Rehabilitation of Classrooms and Chemistry Labs, Miag-ao Campus |  |  | 1115953 | [9 empty] | 0 |  |  | Plan of work forwarded on 02 Sep 2014 to CAS Dean and VCA for approval
30 | Modernization of Academic Labs, Facilities and Equipment-Institute of Fish Processing Technology, College of Fisheries and Ocean Sciences (CFOS), Miag-ao Campus |  |  | 1000000 | [9 empty] | 0 |  |  | CFOS to determine budget utilization
31 | Establishment of New Labs for Nutrition, Physiology and Genetics Repair and Upgrading of Existing Facilities, CFOS, Miag-ao Campus |  |  | 300000 | [9 empty] | 100 |  |  | Completed as of 30 Sep 2014
32 | Modernization of Lab Facilities; Acquisition of New Facilities-Institute of Marine Fisheries and Oceanology, CFOS, Miag-ao Campus |  |  | 200000 | [9 empty] | 0 |  |  | CFOS to determine budget utilization
33 | Conversion of R&D Room into Classroom in Building 3, Wet & Dry Lab, CFOS, Miag-ao Campus |  |  | 98674 | [9 empty] | 0 |  |  | Deferred by end-user; endorsed to CFOS Dean on 12 Dec 2012
34 | Repair of Villadolid Roofing, CFOS, Miag-ao Campus |  |  | 505022 | 116000 | 116000 |  | M-Car Construction & Supply | [5 empty] | 100 |  |  | Completed as of 28 Jun 2014; supply of labor only
35 | Renovation of Pump House Installation; Installation of Seawater Supply System for IA Multi-Species Hatchery, Miag-ao Campus |  |  | 117413 |  |  |  | In-house (CFOS) | [5 empty] | 0 |  |  | Under the supervision of Engineer Gonzales
36 | Renovation/Rehabilitation of Freshwater Aquaculture Station |  |  | 1499998 | 1421414 | 1457423 | [7 empty] | 100 |  |  | Completed as of 11 May 2014
37 | Renovation of Pump House; Installation of Seawater Supply System, Miag-ao Campus |  |  | 117413 | [9 empty] | 0 |  |  | Approved on 06 Nov 2013; to be implemented and supervised by Milkfish Project 2
38 | Construction of Two Lab Counters/Tables at NIMBB Lab, Building 2, Wet & Dry Lab, Miag-ao Campus |  |  | 215016 | 214480 | 235805 |  | Mueda Aggregates | [5 empty] | 100 |  |  | Completed as of 12 Aug 2014
39 | Fabrication of Door Grills, TV Stand, Speaker Stand and Amplifier at AV 107 Pidlaon Hall, Miag-ao Campus |  |  | 27002 |  |  |  | In-house | [5 empty] | 0 |  |  | For implementation, subject to availability of materials
40 | Repair and Conversion of a Stockroom to Soil Quality Lab, IA Hatchery Complex, Miag-ao Campus |  |  | 304006 |  |  |  | In-house | [5 empty] | 0 |  |  | For procurement
41 | Improvement of SOTECH Labs and Classrooms-Labor and Materials |  |  | 1872657 |  |  |  | In-house | [5 empty] | 0 |  |  | For procurement and implementation
42 | Renovation of Audio Visual Room-Tiling of LT Annex Audio Visual Room, Iloilo City Campus |  |  | 131932 |  |  |  | In-house | [5 empty] | 0 |  |  | For implementation
43 | Renovation of CM Comfort Room, Iloilo City Campus |  |  | 288620 |  |  |  | In-house | [5 empty] | 0 |  |  | Work temporarily suspended; to resume upon resolution of mode of procurement for labor
44 | Pantry, CM Faculty Room, CM Building, Iloilo City Campus-Labor and Materials |  |  | 116267 | 114389 | 114389 |  | 1-6-8 Construction & Supply | [5 empty] | 0 |  |  | NTP issued on 08 Aug 2014 but deferred; new NTP to be issued
45 | Fabrication of Fixed Window Screen, College of Management Classrooms, Iloilo City Campus |  |  | 61367 | [9 empty] | 0
46 | Improvement of the Division of Humanities Teaching Facilities, CAS, Miag-ao Campus |  |  | 851000 | 841224 | 841224 |  | 1-6-8 Construction & Supply | [5 empty] | 100 |  |  | Completed as of 25 Nov 2013
47 | Replenishment of Primary Electric Posts, Miag-ao Campus |  |  | 1100000 | 958917 | 958917 |  | Micro Asia Builders Corporation | [5 empty] | 100 |  |  | Completed as of 01 Dec 2013
48 | Wall Partition at Infirmary Consultation Room, Miag-ao Campus |  |  | 74977 | 74977 | 74977 |  | M-Car Construction & Supply | [5 empty] | 100 |  |  | Completed as of Jan 2014
49 | Renovation of CM Faculty Room, Iloilo City Campus |  |  | 335000 | 294944 | 323710 |  | Jaruda Metal Industries | [5 empty] | 100 |  |  | Completed as of 03 Dec 2013
50 | Construction of Multi-Purpose Building (Student Center), Iloilo City Campus |  |  | 1500000 | 1500000 | 1500000 |  | J. Gordon Construction | [5 empty] | 100 |  |  | Completed as of 30 Sep 2014; awaiting turnover of project to UPV
51 | Construction of Ramp at the CAS Building, Miag-ao Campus |  |  | 243894 | 243894 | 243894 |  | In-house | [5 empty] | 100 |  |  | Completed as of 21 Jan 2014
52 | Restoration of the Old High School Building, Iloilo City Campus |  |  | 2000000 | 2000000 | 2000000 |  | DPWH | [5 empty] | 100 |  |  | Completed as of 30 Sep 2014
53 | Retrofitting/Completion of Twin Classroom, Miag-ao Campus |  |  | 369603 | 357294 | 357294 |  | M-Car Construction & Supply | [5 empty] | 100 |  |  | Completed as of 19 Feb 2014
54 | Rehabilitation of Roadways (Asphalt Overlay of Existing UPV Roadways), Miag-ao Campus |  |  | 8811000 | 8700812 | 8700812 |  | G. Uy Construction | [5 empty] | 100 |  |  | Completed as of 20 Jan 2014
55 | Terrace Roof of UPV Executive House, Miag-ao Campus |  |  | 165958 | 165958 | 165958 |  | In-house | [5 empty] | 100 |  |  | Completed as of 30 Apr 2014
56 | Project Rebuild and Tagum River Project Office |  |  | 16824 | 16824 | 16824 |  | In-house | [5 empty] | 100 |  |  | Completed as of Apr 2014
57 | Fabrication of Office Counter, CAS Dean's Office, Miag-ao Campus |  |  | 28170 | 28170 | 28170 |  | In-house | [5 empty] | 100 |  |  | Completed as of 04 Mar 2014
58 | Refurbishing of Old High School Building, Iloilo City Campus |  |  | 866748 | 826163 | 902953 |  | 1-6-8 Construction & Supply | [5 empty] | 100 |  |  | Completed as of 30 Apr 2014; 10% retention released on 15 Jun 2014
59 | 2nd Floor, UPV Alumni Relations, Alumni Lounge, Iloilo City Campus |  |  | 500000 | 500000 |  |  | Topmost Builders | [5 empty] | 100 |  |  | Subtantially completed as of 30 Sep 2014; ready for turnover
60 | Transfer of Electrical Room: Lay Out of Additional Lines and Service Entrance |  |  | 2231510 | 1965437 | 1952419 |  | 1-6-8 Construction & Supply | [5 empty] | 100 |  |  | Completed as of 20 May 2014
61 | Re-channeling (Rerouting of River Flow) and Restoration of Access Road Phase 1: Miag-ao Campus |  |  | 1066620 | 1066620 | 1066620 |  | HLG Construction & Enterprises | [5 empty] | 100 |  |  | Completed as of 20 May 2014
62 | Construction of GCEB/Auditorium Power House and Installation of Electrical Cable from Genset in UPV Iloilo Campus (with Approved Extra Work Order) |  |  | 719557 | 557271 | 614349 |  | Micro Asia Builders Corporation | [5 empty] | 100 |  |  | Completed as of the 2nd week of July
63 | Fabrication of 15 units Double Deck Beds |  |  | 97721 |  | 97721 |  | In-house | [5 empty] | 100 |  |  | Completed as of 22 Aug 2014
64 | Conversion of Classrooms into Laboratory at CAS Basement, Miag-ao Campus |  |  | 1500000 | [9 empty] | 0 |  |  | Plans and project documents forwarded to OVCA thru CAS on 02 Sep 2014
65 | Construction of Intra-School Broadcasting Lab-FM Transmitter, Miag-ao Campus |  |  | 700000 | [9 empty] | 0 |  |  | Preparation of plans/plan of work ongoing
66 | Completion of Diwata Shore Complex, Miag-ao Campus |  |  | 2250000 | [9 empty] | 0 |  |  | Funds to be used for retrofitting; planning stage
67 | Repair of UPV Guest House, Miag-ao Campus |  |  | 572661 | [9 empty] | 0 |  |  | Plans and project documents forwarded to OVCA on 06 Aug 2014; total estimated cost: Php2,647,679.11 (Phase 1-Php1,636,169.13; Phase 2-Php1,011,509.98)
68 | CM Building at Miag-ao Campus |  |  | 107500000 | [9 empty] | 0 |  |  | Perspectives ready
69 | Repainting of CAS Building, Miag-ao Campus | [12 empty] | 0 |  |  | Plans and project documents forwarded to OVCA thru CAS on 21 Jul 2014; estimated project cost-Php971,146.48
70 | Archive Room of the Office of the Registrar, Miag-ao Campus | [12 empty] | 0 |  |  | Awaiting final design of archive rooms
71 | Event Boards for the Iloilo City and Miag-ao Campuses | [12 empty] | 0 |  |  | Plans for comments/recommendations of IPO
72 | Indigenous Center at Center for Western Visayas Studies, Iloilo City Campus |  |  | 2000000 | [9 empty] | 0 |  |  | Preparation of plans/plan of work ongoing
73 | Two-Storey Extension of Covered Court, Miag-ao Campus | [12 empty] | 0 |  |  | Project study and evaluation stage
74 | Roof of the Tennis Court, Miag-ao Campus | [12 empty] | 0 |  |  | Project study and evaluation stage
75 | Rehabilitation/Upgrading of Pilot Plant, Institute of Fish Processing Technology, CFOS | [5 empty] | UP System: President's Initiatives | [6 empty] | 0 |  |  | Approved on 04 Nov 2014
76 | Renovation/Rehabilitation of Fish Biology Lab 1 at the Wet and Dry Lab, Miag-ao Campus |  |  | 500000 |  |  | UP System: President's Initiatives | [6 empty] | 0 |  |  | Approved on 04 Nov 2014
77 | Evaluation/Repair of the Seawater Intake, Wet and Dry Laboratory, Miag-ao Campus |  |  | 191000 |  |  | UP System: President's Initiatives | [6 empty] | 0
78 | Repair of Rusted/Leaking Galvanized Roof of Buildings 1&2, Wet and Dry Lab, Miag-ao Campus |  |  | 400000 |  |  | UP System: President's Initiatives | [6 empty] | 0
79 | Improvement of Lab Areas, Conversion of Vacant Spaces into Additional Labs and Lab Support Services in Building 2, Wet and Dry Lab, Miag-ao Campus |  |  | 300000 |  |  | UP System: President's Initiatives | [6 empty] | 0
80 | Replacement of Bathroom Fixtures in Buildings 1&2 with Industrial Type, High Pressure Fixtures; Replacement of Bathroom Tiles; Improvement of the Condition of the Comfort Rooms for both Buildings |  |  | 250000 |  |  | UP System: President's Initiatives | [6 empty] | 0
81 | Upgrading of GIS Lab Equipment/Computers and Replacement of Parts-Iloilo City, Miag-ao and Tacloban Campuses |  |  | 500000 |  |  | UP System: President's Initiatives | [6 empty] | 0
82 | Landscaping of Campus Grounds in Iloilo City and Miag-ao Campuses |  |  | 300000 |  |  | UP System: President's Initiatives | [6 empty] | 0
0
393 | Expansion of Intra School Broadcasting Lab Room (CAS) & Upgrading of Broadcast Communication Labs (CAS-Humanities) |  |  |  | 733000 |  |  | Various suppliers | [5 empty] | 100 |  |  | Completed as of 30 May 2014
393 | Improvement of Classroom and Acquisition of Facilities (Division of Humanities) |  |  |  | 841224 |  |  | 1-6-8 Construction & Supply | [5 empty] | 100 |  |  | Completed as of 25 Nov 2013
393 | Modernization of Academic Laboratory Facilities (Institute of Fish Processing Technology-IFPT) |  |  |  | 1004014 |  |  | Various suppliers | [5 empty] | 100 |  |  | Completed as of October 2014
393 | Establishment of Three (3) New Labs: Nutrition, Physiology, and Genetics; Repair and Upgrading of Existing Facilities |  |  |  | 291220 |  |  | M-Car Construction & Supply and Emcor | [5 empty] | 100 |  |  | Completed as of Feb 2014
393 | Modernization and Acquisition of Lab Facilities (Institute of Marine, Fisheries and Oceanology) |  |  |  | 203000 |  |  | PHILAB Industries and various other suppleirs | [5 empty] | 100 |  |  | Completed as of 04 Sep 2013
393 | Conversion of Common Dining Hall into the Graduate Conference Hall |  |  |  | 984152 |  |  | Early Riser Construction | [5 empty] | 100 |  |  | Completed as of 30 Sep 2013
394 | Rehabilitation of Roadways |  |  |  | 8708234 |  |  | G. Uy Construction | [5 empty] | 0 |  |  | Completed as of 20 Jan 2014
394 | Replacement of Primary Electric Post |  |  |  | 958916 |  |  | MICRO-Asia Builders | [5 empty] | 0 |  |  | Completed as of 01 Dec 2013
438 | Expansion of IntraSchool Broadcasting Lab Room | [12 empty] | 0
438 | Upgrading of Broadcast Communication Labs, CAS-Division of Humanities | [12 empty] | 0
438 | Improvement of Classroom and Acquisition of Facilities, CAS-Humanities | [12 empty] | 100 |  |  | Completed as of 25 Nov 2013
467 | Wet Process |  |  | 1300000 | [9 empty] | 0
467 | Hot Process |  |  | 800000 | [9 empty] | 0
467 | Repair/Reconditioning of Different Existing Equipment |  |  | 400000 | [9 empty] | 0
467 | Purchase of Chemicals, Supplies and Utensils to be used of the Initial Income-generating Projects |  |  | 200000 | [9 empty] | 0